## Slide 1
LIGHTHOUSE LABS
Jahidul Islam Jony 0112330060
Partha Protim Podder 0112331079
Mahin Hasan Upol 0112220520
Sourav Saha 0112330638
Saptarshi Biswas Supty 0112330221

## Slide 2
PMI PROJECT MANAGEMENT CASE STUDY
LIGHTHOUSE LABS
Innovating in a Crisis
Scaling COVID-19 testing capacity 200x in a matter of months —
lessons in agility, lean process, and crisis leadership

## Slide 3
ARTICLE OVERVIEW
A Crisis Demanded a New Kind of Lab
When COVID-19 struck in spring 2020, the Scottish government urgently needed to scale diagnostic testing capacity.
The Lighthouse Laboratory was created as a partnership among the UK Government, Scottish government, University of Glasgow, the NHS, and private industry.
On day one, the lab processed just 41 tests — it needed to reach a sixteen-fold increase in capacity within 3–4 months.
The article's core idea: achieving that kind of scale normally takes years — this project shows how project management tools compressed that timeline into months.
WHY IT MATTERS FOR PM
Lighthouse Labs is a real-world case of applying Agile, Lean, and Theory of Constraints principles to scale an operation under extreme time pressure — with lives on the line.
16x
capacity increase targeted in just 3–4 months
(typically a multi-year undertaking)
2

## Slide 4
PROJECT & SYSTEM CONTEXT
One of the UK's Largest COVID Testing Facilities
Hosted by the University of Glasgow at the Queen Elizabeth University Hospital campus.
Repurposed from an existing research laboratory into a high-throughput diagnostic testing facility.
Identified after Jerome Finlayson (Scottish Manufacturing Advisory Service) engaged the Scottish government on how to reach the needed scale.
Now capable of processing 85,000 tests within a 24-hour turnaround.
University of
Glasgow
NHS
Dept. of Health
& Social Care
Bio Clavis
(industry)
LIGHTHOUSE
LAB
3

## Slide 5
KEY PROJECT MANAGEMENT CONCEPT
From a 12-Week Plan to an Agile Cadence
Leadership initially built a comprehensive 12-week project plan — a traditional, predictive approach.
The pandemic's dynamic, fast-changing environment made a rigid long-range plan impractical almost immediately.
BEFORE
Comprehensive
12-Week Plan
Predictive, waterfall-style planning
Fixed long-range milestones
>
AFTER
Kaizen &
Focused Improvement Teams
Clear objectives set daily and weekly
Tight Plan > Do > Check > Act cycles to iterate as conditions changed
4

## Slide 6
KEY PROJECT MANAGEMENT CONCEPT
Theory of Constraints: Managing the Bottleneck
5 FOCUSING
STEPS
1
2
3
4
5
Identify
the constraint
Exploit
the constraint
Subordinate
everything else
Elevate
the constraint
Repeat —
find the next one
THE BOTTLENECK, IN PRACTICE
Time was the lab's greatest operational cost — TOC gave a structured way to attack it.
Some bottlenecks can't be removed. Opening a sample box always takes time.
But that step could still be standardized — every worker, every shift, opened boxes the same way, in the same amount of time.
Managing (not eliminating) the constraint kept throughput predictable at scale.
5

## Slide 7
KEY PROJECT MANAGEMENT CONCEPT
Standard Work + Short Interval Control
SW
Standard Work
In the first weeks, work wasn't understood, reliable, or repeatable — output was inconsistent.
The lab introduced identical modular workstations for every worker.
Clear instructions and structured training turned tribal knowledge into a repeatable process.
Result: predictable, sustainable performance instead of a one-off "brute-force" push.
SIC
Short Interval Control
Progress at key bottlenecks was reviewed in brief units — e.g., hourly — not weekly.
Problems were caught and iterated on almost as soon as they appeared.
This tight feedback loop is what made continuous Plan-Do-Check-Act cycles possible in practice.
6

## Slide 8
MANAGEMENT APPROACH
Hybrid — Whatever Works
A compelling, urgent mission attracted an enormous volunteer workforce almost overnight.
That sense of purpose was a critical motivator through long hours and a steep learning curve.
Management blended traditional planning, Lean manufacturing tools, and Agile iteration — choosing whatever approach fit the moment, rather than following one methodology dogmatically.
750
volunteers
220
roles filled
PLAN > DO > CHECK > ACT
PLAN
DO
CHECK
ACT
repeat
7

## Slide 9
MANAGEMENT APPROACH
Stakeholder Management
With many partners and a mission-critical goal, stakeholder attention had to be prioritized, not spread evenly.
The team kept close, frequent contact with elected officials and other high-influence, high-interest parties.
Remaining stakeholders were segmented by their level of interest and power — so effort matched impact.
Keep
Informed
Manage
Closely
Keep Into
Account
Meet Their
Needs
Power / Influence of Stakeholder →
Level of
Interest ↑
8

## Slide 10
CHALLENGES & RISKS
Growing Fast Without Breaking
1
Unsustainable Scaling
By June, 5,000 tests/day was hit through brute force — a pace the team knew could not hold long-term.
2
No Standard Process
Early on, workers lacked understood, reliable, predictable ways of working, causing inconsistent throughput.
3
Steep Learning Curve
Hundreds of volunteers had to be trained fast on unfamiliar, high-stakes diagnostic work.
4
Multi-Partner Coordination
Government, university, NHS, and industry stakeholders all had different needs and priorities to balance.
9

## Slide 11
RESULTS
From 41 to 85,000 Tests
41
tests on Day 1
of operation
5,000
tests/day by June —
reached by brute force
85,000
tests within a
24-hour turnaround, today
A sixteen-fold increase achieved in months, not the years such scaling would normally take.
10

## Slide 12
LESSONS LEARNED
Process Lessons — and Human Ones
PROCESS & MANAGEMENT
Reviewing progress at the shortest useful interval keeps small problems from becoming big ones.
Clear roles, structured process, and management attention are foundational to scale.
Regular reflection ("stop and check") is what makes continuous improvement possible.
THE HUMAN DIMENSION
"Stop getting into the drama of situations" — don't let emotion derail problem-solving.
Protect positive energy, flexibility, and trust between teammates under pressure.
People sustain a crisis response as much as process does — culture is not optional.
11

## Slide 13
KEY TAKEAWAYS
What Project Managers Should Remember
1
In a crisis, agility beats a rigid long-range plan — pivot from waterfall to iterative cycles fast.
2
Lean tools (Kaizen, Theory of Constraints, Standard Work) scale real operations, not just factories.
3
You can't always remove a bottleneck — but you can standardize and manage it.
4
Segment stakeholders by power and interest so limited attention goes where it matters most.
5
Culture and human factors are as decisive as process when the pressure is highest.
12

## Slide 14
Thank You
Questions & Discussion
Source: Project Management Institute — "Lighthouse Labs: Innovating in a Crisis" Case Study