# PMG 4101 – Mid-Term Exam (Fall 2024)

# Methodology Choice & Drawbacks of SCRUM:

Chosen Methodology: Agile (SCRUM) Methodology

Given the scenario described, Agile methodology using the SCRUM framework is the most appropriate approach for this project. Below is a detailed explanation of why Agile is chosen and the rationale behind it:

Rationale for Choosing SCRUM (Agile Methodology)

- Project Complexity and Evolving Requirements:

The project involves a complex e-learning platform that will utilize AI/ML algorithms for personalized learning. With evolving features such as gamification, social learning tools, and real-time collaboration, Agile allows flexibility to adapt to these changes.

The client wants to incorporate features incrementally, starting with the most important ones. SCRUM allows for iterative development, where new features are added after each sprint, ensuring flexibility and continuous improvement.

- Early Delivery of Core Features:

The client has Mid (Fall-24) File requested the platform be ready for a pilot program within four months. Using SCRUM, the team can deliver the core functionalities within the first few sprints and continue to enhance and scale the platform over time. This ensures quick wins for the client and stakeholders.

- Cross-functional Team Collaboration:

The project requires expertise in areas like AI/ML, UX design, and gamification, which the current team lacks. With Agile, the team can integrate specialists (e.g., data scientists, instructional designers) into the project at various points and collaborate closely with subject matter experts. Agile encourages collaboration across roles, ensuring better-quality outcomes.

- Frequent Feedback and Continuous Improvement:

The platform will be developed with continuous input from teachers, students, and other stakeholders, ensuring it meets the target audience’s needs. In SCRUM, frequent sprints and reviews will enable the team to make necessary adjustments and improvements based on user feedback. This process ensures that the platform remains aligned with educational goals and student needs.

- Risk Management and Scalability:

Given the concerns about balancing quality and scalability, SCRUM helps manage these risks by breaking the project into smaller, manageable chunks. Each sprint allows the team to focus on specific modules and their scalability, ensuring that the platform can handle high traffic during peak usage periods.

Drawbacks of SCRUM Methodology:

- Requires Constant Communication:

SCRUM requires constant communication between all stakeholders, team members, and clients. This might not always be feasible if the team is spread out or lacks clear communication channels, potentially slowing down the development process.

- Steep Learning Curve for New Team Members:

The SCRUM framework can be complex for new team members, especially if they are unfamiliar with Agile practices. This might delay the start of the project or create confusion within the team.

- Difficulty in Estimation:

In SCRUM, it can be challenging to accurately estimate how long tasks will take, especially in complex projects like an AI-driven e-learning platform. Misestimations can lead to delays and missed deadlines, especially when multiple sprints are involved.

- Dependency on Scrum Master:

The success of SCRUM depends heavily on the Scrum Master to facilitate the process. If the Scrum Master is not experienced or does not manage the team well, the process could break down, leading to inefficiencies and miscommunication.

When SCRUM is Ideal:

SCRUM is ideal for projects with:

- Changing requirements that evolve over time.

- Continuous stakeholder feedback and involvement.

- A need for rapid delivery of features and early product launches.

- Complex projects that involve multiple features and require flexibility in development.

In contrast, SCRUM may not be the best fit for projects with fixed, well-defined requirements or where extensive documentation and clear, linear progress are needed.

# Vision and Scope Document:

- Vision Document Outline:
    2.1 Introduction:
    	- Project Overview: The project aims to develop a personalized e-learning platform that uses AI to adapt learning content to students' individual needs, integrating gamification and real-time collaboration tools to increase student engagement and improve learning outcomes.
   	 - Purpose: The platform is designed to create a customized learning experience, making it more engaging and efficient for students, improving learning outcomes, and reducing dropout rates.
    	- Scope: 
        	- Features: AI-driven learning paths, gamified elements, adaptive quizzes, real-time feedback, social learning tools.
        	- Target Audience: High school and university students.

    2.2 Stakeholders:
    		- Primary Stakeholders: Students, educators, school administrators.
    		- Secondary Stakeholders: Instructional designers, AI/ML specialists, software developers, project managers.

    2.3 Objectives:
    	- Main Objectives:
        	1. Provide a personalized learning experience using AI-driven recommendations.
        	2. Enable real-time feedback on student performance.
        	3. Incorporate gamification (badges, progress tracking) to keep students motivated.
        	4. Implement adaptive quizzes that adjust in difficulty based on student progress.
       		 5. Allow real-time collaboration among students.
       		 6. Develop a scalable platform that can handle high traffic during peak usage periods.

    2.4 Constraints:
   		 - Time Constraint: The initial pilot program must be released within four months, with the full platform completed within one year.
    		- Technical Constraints: Integrating AI for personalized learning paths and real-time monitoring could present technical challenges.
    		- Budget Constraint: Hiring AI engineers, instructional designers, and other specialists within budget.

    2.5 Deliverables:
    	- Initial Deliverables:
        	- AI-driven personalized learning paths.
        	- Basic gamification elements (e.g., badges and progress tracking).
        	- Adaptive quizzes and feedback system.
    - Final Deliverables:
             - Full platform with social learning tools and real-time collaboration features.
             - Multilingual support for English, Bangla, and French.

Scope Document Outline:
    1. In-Scope:
         	- Development of core features: adaptive quizzes, AI learning paths, real-time feedback, and gamification.
        	- Social learning tools and real-time collaboration features.
        	- Multilingual support for English, Bangla, and French.
    2. Out-of-Scope:
        	- Features like virtual classrooms, student-teacher communication tools, or third-party integrations with other platforms will be excluded in the initial release.

3. Functional Requirements:
    		- AI-Driven Learning Paths: 
        	- Machine learning algorithms will be used to personalize learning content based on the student’s pace and style.
    		- Gamification: 
       		 - Incorporation of badges, leaderboards, and progress tracking.
    		- Real-Time Feedback: 
        	- Students will receive instant feedback on their answers and progress.
    		- Social Learning Tools: 
        		- Discussion forums, group projects, peer reviews.

4. Non-Functional Requirements:
    - Scalability: The software must handle a large number of users simultaneously, especially during peak exam periods.
    - Security: The system must ensure secure data handling and prevent cheating or violations during exams.
    - Performance: The system must operate with minimal delay, especially for real-time monitoring.
    - Accessibility: The platform should be accessible on various devices, including desktops, laptops, and mobile phones.

5. Assumptions:
    - The platform will initially support English, Bangla, and French, with plans to expand language options later.
    - The development team will be equipped with the necessary expertise to integrate AI/ML technologies for the learning path.

6. Exclusions:
    - Social media integration or external integrations are excluded from the initial release.
    - Features like advanced analytics for course performance will be considered in future releases.

# WBS Rules & Development:

WBS for the Project:
    1. Platform Development:
        - Task 1.1: Interactive Content Development
            - Develop educational modules and content for various subjects (high school to university level).
            - Include text, images, videos, and interactive media to engage learners.
        - Task 1.2: Adaptive Quizzes
            - Implement a quiz system that adapts based on student performance.
            - Design different types of questions (multiple choice, true/false, open-ended).
        - Task 1.3: Personalized Learning Paths
            - Implement a system that tailors learning content to individual student needs.
            - Use machine learning algorithms to adjust the content based on progress.
        - Task 1.4: Collaborative Learning Tools
            - Build features for group discussions, shared notes, and peer reviews.
            - Integrate real-time collaboration features for students and educators.
        - Task 1.5: Gamification Elements
            - Design and implement progress tracking and achievement badges.
            - Develop leaderboards and other gamified features to increase engagement.
        - Task 1.6: Real-Time Feedback
            - Implement real-time feedback functionality to help students track their performance.
            - Provide instant feedback for quizzes, assignments, and activities.
        - Task 1.7: Scalability and Performance
            - Ensure the platform can handle high traffic and peak usage during exams.
            - Test and optimize server capacity to handle many concurrent users.

    2. AI/ML Integration:
        - Task 2.1: Machine Learning for Personalization
            - Develop machine learning models to personalize content and quizzes based on learning styles and preferences.
        - Task 2.2: Data Collection and Analytics
            - Set up systems to collect data on user behavior, quiz performance, and learning habits.
            - Implement data analysis tools to process this data for improvements in the system.

    3. Security and Data Protection:
        - Task 3.1: Secure Login and Authentication
            - Implement secure user login with multi-factor authentication (MFA).
            - Integrate password recovery and user session management features.
        - Task 3.2: Data Encryption
            - Ensure all sensitive data (user information, quiz results, payment data) is encrypted.
            - Implement secure data storage and secure data transmission methods.
        - Task 3.3: Payment Gateway Integration
            - Integrate a secure payment gateway for premium features or course purchases.

    4. Testing and Deployment:
        - Task 4.1: Automated Testing
            - Develop automated tests for core platform functionalities like quizzes, feedback, and login.
        - Task 4.2: Manual Testing
            - Conduct manual testing to ensure the platform is user-friendly and meets educational standards.
        - Task 4.3: Bug Fixing and Optimization
            - Address any issues identified during testing and optimize performance.
        - Task 4.4: Deployment and Go-Live
            - Deploy the platform to production and ensure all functionalities are running smoothly.

    5. Future Enhancements (Optional):
        - Task 5.1: Self-Driving Car Features (Future Phase)
            - Implement AI-driven self-driving functionalities for the vehicle showcase (future feature).
        - Task 5.2: Social Learning Features
            - Add social features like forums, live chat, or student-teacher communication tools.

Estimating Duration for Major WBS Components:
    The estimated duration for the major WBS components is as follows (unit in months):

    1. Platform Development:
        - Task 1.1: Interactive Content Development - 1 month
        - Task 1.2: Adaptive Quizzes - 1.5 months
        - Task 1.3: Personalized Learning Paths - 2 months
        - Task 1.4: Collaborative Learning Tools - 1.5 months
        - Task 1.5: Gamification Elements - 2 months
        - Task 1.6: Real-Time Feedback - 1 month
        - Task 1.7: Scalability and Performance - 2 months
        Total for Platform Development: 11 months

    2. AI/ML Integration:
        - Task 2.1: Machine Learning for Personalization - 2 months
        - Task 2.2: Data Collection and Analytics - 1.5 months
        Total for AI/ML Integration: 3.5 months

    3. Security and Data Protection:
        - Task 3.1: Secure Login and Authentication - 1 month
        - Task 3.2: Data Encryption - 1.5 months
        - Task 3.3: Payment Gateway Integration - 1 month
        Total for Security: 3.5 months

    4. Testing and Deployment:
        - Task 4.1: Automated Testing - 2 months
        - Task 4.2: Manual Testing - 1 month
        - Task 4.3: Bug Fixing and Optimization - 1 month
        - Task 4.4: Deployment and Go-Live - 1 month
        Total for Testing and Deployment: 5 months

    1.3 Estimated Total Project Duration:
    Summing up the major components:

    Platform Development: 11 months
    AI/ML Integration: 3.5 months
    Security and Data Protection: 3.5 months
    Testing and Deployment: 5 months

    Total Estimated Duration: 23 months (assuming all features are implemented and no major delays)

# Delphi Wideband Estimation (DWE):

# The Delphi Wideband Estimation (DWE) technique is an estimation method used in project management to determine the effort, duration, or resources required for a task. It involves a group of experts providing independent estimates for each task, followed by a group discussion to refine those estimates and reach a consensus. This method is particularly useful in complex projects, like the development of an e-learning platform, where experts from different areas contribute valuable insights.

# Steps of the Delphi Wideband Estimation (DWE) Process:

# 1. Assemble Tasks

# Activity:

# The project manager assembles a team of three experts for estimating the tasks in the e-learning platform project.

# Tasks are clearly defined, such as "Develop interactive content," "Integrate gamification elements," "Build AI-driven learning paths," etc.

# Example Task: Develop interactive content for the platform.

# 2. Initial Estimation by Experts

# Activity:

# Each expert provides their independent estimates for the time or effort required for each task. These are given anonymously to avoid bias from groupthink or influential team members.

# Example:

# Task 1: Develop interactive content for the platform

# Expert 1 estimates: 15 days

# Expert 2 estimates: 18 days

# Expert 3 estimates: 14 days

# 3. Group Discussion and Clarification

# Activity:

# After the initial estimates are collected, the project manager organizes a group discussion to review the estimates and clarify any discrepancies or ambiguities.

# Each expert explains the rationale behind their estimates, and any misunderstandings or assumptions are discussed and addressed.

# Example:

# Expert 1 might explain their estimate is based on the complexity of creating interactive quizzes.

# Expert 2 could suggest that additional time is needed for content integration across different learning paths.

# 4. Re-estimation and Refinement

# Activity:

# After the discussion, each expert revises their estimate based on the information shared during the group discussion. This process allows the estimates to be refined and adjusted according to new insights.

# Example:

# Expert 1 revises their estimate to 17 days for content development.

# Expert 2 revises their estimate to 19 days, and Expert 3 revises to 16 days.

# 5. Final Estimation and Consensus

# Activity:

# The experts revise their estimates one more time based on the discussion and any new information shared.

# A consensus is reached on the final estimate for the task.

# Final Estimate:

# After the discussion, the team agrees on a final estimate of 17 days for developing interactive content.

# Estimation Form and Tentative Convergence Chart

# The estimation form captures the estimates and final consensus for each task. It also records the comments from the experts.

# Estimation Form Example:

| # Task | # Expert 1 Estimate | # Expert 2 Estimate | # Expert 3 Estimate | # Final Estimate | # Comments |
| --- | --- | --- | --- | --- | --- |
| # Develop Interactive Content | # 15 days | # 18 days | # 14 days | # 17 days | # Complexity of content and interactivity |
| # Integrate Gamification Elements | # 12 days | # 14 days | # 13 days | # 13 days | # Integration with existing platform |
| # Build AI-driven Learning Paths | # 20 days | # 18 days | # 22 days | # 20 days | # AI complexity and content tailoring |

# Tentative Convergence Chart:

# The convergence chart shows how the estimates evolve across the iterations. The y-axis represents the number of days, and the x-axis represents the estimation rounds. After each discussion and revision, the estimates converge toward a final value.

| # Iteration | # Expert 1 | # Expert 2 | # Expert 3 | # Final Estimate |
| --- | --- | --- | --- | --- |
| # 1st Round | # 15 days | # 18 days | # 14 days |  |
| # 2nd Round | # 17 days | # 19 days | # 16 days |  |
| # Final | # 17 days | # 19 days | # 16 days | # 17 days |

# This convergence chart helps visualize how the estimates become more consistent over time as experts discuss and revise their initial estimates.

- Risk Plan Sheet:

| ID | Risk (what could go wrong) | Category | P | I | Priority |  |  | Early indicators |  | Mitigation & response |  | Owner |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Timeline compression: pilot in 4 months causes quality gaps and rework | Schedule/Scope |  | 4 |  | 5 | 20 |  | Sprint spillover rises; defect escape rate up; burn-down flat |  | Reduce: freeze MVP scope two sprints before pilot; MoSCoW prioritization; feature flags; tighten DoD. Avoid: move lower-value items to Release 2. |  | Project Manager |  |
| R2 | AI/ML skill gap delays personalization engine and analytics | People/Skills | 4 | 4 | 16 |  |  | Open roles > 30 days; missed ML spikes; prototype accuracy below target |  | Reduce: parallel hiring plus short-term contractor; start rules-based personalization; stage ML to Phase-2; pair AI hires with devs for knowledge transfer. |  | Eng. Manager |  |
| R3 | Scalability failure during peak usage (timeouts, slow quiz feedback) | Performance | 3 | 5 | 15 |  |  | 95p latency > SLO; CPU/memory saturation; queue backlog |  | Reduce: load tests with exam-week traffic shape; autoscaling; DB indexing & caching; CDN; circuit breakers and graceful degrade. Transfer: cloud SLAs. |  | DevOps Lead |  |
| R4 | Data privacy/compliance issues with student data and analytics | Compliance | 3 | 5 | 15 |  |  | DPO/legal flags; unclear retention map; vendor without DPA/SCCs |  | Avoid/Reduce: DPIA; data minimization; regional storage; encryption in transit/at rest; RBAC; audit logs. Transfer: signed DPAs and SCCs. |  | Compliance Officer |  |
| R5 | Engagement shortfall: weak UX/gamification fails to improve outcomes | Product/UX | 3 | 4 | 12 |  |  | Low DAU/WAU; short sessions; low badge completion; NPS drops |  | Reduce: hire UX + instructional designer; A/B test micro-interactions; small frequent UX releases; align badges to learning outcomes; student/teacher reviews. |  | Product Owner |  |
| R6 | Third-party dependency outage (auth, payments, NLP, translation) | Vendor | 3 | 4 | 12 |  |  | Provider status red; 5xx spikes; rate-limit hits |  | Reduce/Transfer: multi-provider or cached fallback; retry queues; back-pressure; strict SLAs and error budgets; synthetic monitoring of vendor APIs. |  | Platform Lead |  |
| R7 | Integration complexity across modules (content, quizzes, social, analytics) | Architecture | 3 | 4 | 12 |  |  | Cross-team blockers; merge conflicts; contract breaks |  | Reduce: versioned API contracts; consumer-driven contract tests; weekly integration build; architecture review gate for cross-module changes. |  | System Architect |  |
| R8 | Quality regressions due to rushing features for pilot | Quality | 3 | 4 | 12 |  |  | Escaped defects; rising hotfix count; flakey tests |  | Reduce: test pyramid with CI; canary releases; definition of ready/done; bug SLAs; exploratory test cycles before pilot. |  | QA Lead |  |
| R9 | Budget overrun from AI/UX hiring and infra for scale | Cost | 3 | 3 | 9 |  |  | Cloud bill > forecast; extended contractor hours |  | Reduce: FinOps guardrails; autoscaling quotas; storage lifecycle policies; time-boxed discovery spikes; ROI review per feature before scaling. |  | PM + Finance |  |
| R10 | Stakeholder misalignment on MVP vs nice-to-have features | Stakeholders | 3 | 3 | 9 |  |  | Late change requests; unclear acceptance criteria |  | Reduce: fortnightly demos; change control board; signed MVP acceptance criteria; transparent release roadmap. |  | Project Manager |  |