# Mid Term Exam Solution (Spring-25)

# PMG 4101: Project Management

# Methodology Selection & Justification:

Methodology Chosen: Agile Methodology

Given the scenario, Agile is the most appropriate software engineering methodology for developing the software for the Electric Vehicle (EV) project. Below is the rationale for choosing this methodology:

Iterative Development: The project is vast, and the scope could evolve with the introduction of new features. Agile allows for incremental development, where the team can build a module at a time and evaluate its functionality with the client, which suits the changing needs of the EV market. This allows for more flexibility and ensures continuous delivery of functional software.

Client Involvement and Feedback: Since the client requires constant updates and the ability to add new features, Agile enables frequent meetings and feedback loops after each module is completed, ensuring that the software aligns with the client’s evolving requirements.

Risk Management: The project has various risks, including security concerns and future requirements for AI/ML systems. Agile allows the team to respond quickly to new risks and adapt the system by re-prioritizing features in successive sprints.

Team Collaboration: With modules related to platform, EV software, security, and AI/ML systems, Agile fosters collaboration across diverse teams, such as data science specialists and security experts, ensuring that all components are given proper attention.

Scalability: The software may need to scale in the future to include more vehicles beyond cars. Agile allows the team to gradually add new features and accommodate these changes without disrupting the development of the core system.

Rationale for Choosing Agile Over Waterfall:

Waterfall methodology, while structured, is more rigid and doesn’t allow for changes once the requirements are defined. Given the evolving nature of the project and the market’s dynamic features, Agile's flexibility makes it a better fit. However, in cases where the project is well-defined, the requirements are fixed, and the client is unlikely to request changes, Waterfall might be more suitable. For example, if the client had requested only the core features without any future expansion or updates, Waterfall could have been considered.

When Waterfall Would Be More Appropriate:

Waterfall would be more suitable for projects with clearly defined requirements that are unlikely to change during the development process. Examples include:

- Government Software Projects: When the project scope is predefined, with strict requirements and regulations that do not allow for flexibility.

- Fixed-scope Systems: Projects that involve building a system with no expected changes in the future, like certain hardware integration systems or infrastructure projects.

In contrast to Agile, Waterfall’s linear and sequential structure would be better in these cases where changes and iterations are not expected.

# Vision and Scope Document:

Vision Document for Electric Car Brand Software:

1.1 Introduction:

- Project Overview: The project involves the development of a comprehensive software system for a new Electric Vehicle (EV) brand. The software will showcase the cars, their features, allow for car sales, and incorporate functionalities such as locating nearby charging stations and recommending routes. Initially, AI-driven self-driving features are excluded due to budget and time constraints. However, the platform is designed to be modular, with the potential for future expansion.

- Purpose: The primary goal is to provide seamless experience for customers interested in purchasing and using electric vehicles. The platform should enhance the customer's journey, from exploring vehicle options to purchasing and utilizing charging stations. This solution will also collect customer feedback and data to allow the company to continually improve the software and stay competitive in the evolving EV market.

- Scope:

- Features: The platform will initially include car showcasing, feature descriptions, car sales functionalities, charging station pathfinding, and customer feedback collection.

- Target Audience: The primary users will be potential customers (EV buyers) and the business team managing car sales and customer feedback.

1.2 Stakeholders:

- Primary Stakeholders:

- Customers (EV Buyers): They will use the platform to explore car options, make purchases, and find charging stations.

- Business Group (Client): They are responsible for providing the overall direction and requirements for the software, including sales processes and customer data analysis.

- Secondary Stakeholders:

- Development Team: This team will be responsible for creating the software platform, including the web application and AI integrations.

- AI/ML Specialists: To implement future AI-driven features, such as self-driving cars and advanced recommendations based on user data.

- Data Scientists: To create systems for collecting and analyzing customer feedback and vehicle usage statistics.

1.3 Objectives:

- Develop an intuitive, user-friendly platform to showcase EV models and their features.

- Integrate real-time car sales and inventory management functionality.

- Include a system that helps customers find nearby charging stations and recommend routes based on location.

- Ensure the platform can be scaled to include other vehicle types and additional features in the future.

- Build a system that collects customer feedback to identify key features for future development.

- Implement AI-driven features in future releases as the project expands.

1.4 Constraints:

- Time Constraint: The initial platform is expected to be delivered within 4 months for a pilot program, with a full product expected in 12 months.

- Budget Constraint: Due to budget limitations, certain advanced features, such as AI for self-driving cars, have been excluded from the first version of the platform.

- Technological Constraints: Integrating AI systems for features like self-driving cars will require more development time and resources in future phases.

1.5 Assumptions:

- Availability of Resources: The client will provide the necessary resources, including subject matter experts (SMEs), AI engineers, and data scientists when needed.

- Platform Scalability: The platform will be designed to handle increased user demand, especially as the project evolves to incorporate other vehicles beyond cars.

1.6 Deliverables:

- Initial Deliverables:

- A working platform showcasing the vehicles, their features, and sales functionalities.

- A system to find charging stations and recommend routes for users.

- A customer feedback system to collect data for future improvements.

- Final Deliverables:

- A fully integrated platform that includes other vehicle types.

- Advanced AI-driven features, such as self-driving assistance, once future resources allow.

Scope Document Outline:

2.1 Project Scope Statement:

- In-Scope:

- **Car Showcase and Sales Functionality**: The platform will allow users to view vehicle models, their features, and purchase options.

- **Charging Station Finder**: The software will provide a feature that shows nearby charging stations and suggests the best route for reaching them

- **Customer Feedback System**: A customer feedback mechanism should be in place to collect data on user satisfaction, desired features, and issues with the platform.

- **Modular Structure**: The system will be designed to accommodate additional vehicles and features in future updates.

- Out-of-Scope:

- **Self-Driving AI**: The self-driving feature is excluded in this phase due to budget and time constraints.

- Third-Party Integrations**: Integration with third-party services or platforms (such as social media or external data providers) is out of scope for the initial release.

2.2 Functional Requirements:

- **Car Showcase**: The platform should display detailed information about each vehicle model, including features, pricing, and availability.

- **Sales Functionality**: The platform should facilitate online transactions, managing orders, and providing a secure payment gateway.

- **Charging Station Finder**: Users should be able to search for nearby charging stations and get real-time route recommendations.

- **Customer Feedback**: A system should be built to gather user feedback, focusing on features they like, issues they encounter, and suggestions for improvements.

2.3 Non-Functional Requirements:

- **Scalability**: The platform must be able to scale to accommodate additional vehicles beyond cars, once the project is expanded.

- **Security**: The software must ensure that customer data, especially payment and personal information, is kept secure.

- **Performance**: The platform must be responsive and able to handle a high number of concurrent users, especially during peak sales periods.

- **Usability**: The interface should be intuitive for users to browse vehicles, make purchases, and locate charging stations.

2.4 Assumptions:

- The platform will be developed with the necessary expertise in AI, machine learning, and software development.

- The system will integrate with a reliable database to manage car listings, customer information, and charging station locations.

2.5 Exclusions:

- **Advanced Features**: Features like vehicle-to-grid technology, advanced telematics, or third-party service integration will be excluded from the initial release.

- **Self-Driving AI**: The AI component for self-driving cars is deferred due to time and budget constraints.

# Work Breakdown Structure (WBS):

# WBS for the Project:

1. Platform Development:

-Task 1.1: Car Showcase Module

- Develop the interface to showcase available vehicles

- Include vehicle descriptions, specifications, and pricing

- Implement image galleries and video showcases for each car model

- Task 1.2: Sales Functionality

- Develop e-commerce features for online car sales

- Integrate secure payment gateway for transactions

- Develop order management system (order processing, confirmations)

- Task 1.3: User Account Management

- Implement user authentication and registration

- Set up user profile management functionality (personal info, order history)

- Enable password recovery and account settings

- Task 1.4: Vehicle Inventory Management

- Set up a system to manage car inventory

- Integrate the system with the sales module to track stock levels in real-time

- Build a dashboard for sales staff to monitor inventory

2. Charging Station Finder:

- Task 2.1: Charging Station Database Integration

- Develop or integrate a database for nearby charging stations

- Collect real-time data on charging station availability, types, and locations

- Task 2.2: Route Recommendation System

- Build an algorithm to recommend optimal routes to charging stations

- Use GPS data and real-time traffic updates to suggest routes

- Integrate map APIs for user-friendly route displays

3. AI/ML Integration (For Future Use):

- Task 3.1: AI System for Self-Driving

- Design AI systems to enable self-driving functionalities (future feature)

6            - Implement sensors and cameras for real-time environment analysis

- Implement machine learning models for driving decision-making

- Task 3.2: Data Collection and Analytics for AI

- Set up systems for collecting data on user behavior and vehicle usage

- Implement data analysis tools to improve AI learning and future features

- Build feedback loops for continuous AI model improvement

4. Security and Data Protection:

- Task 4.1: Secure Payment Gateway Integration

- Integrate third-party payment systems like PayPal, Stripe, etc.

- Ensure secure transaction processing with encryption and compliance to data protection regulations.

- Task 4.2: Data Security and Encryption

- Implement end-to-end encryption for sensitive user data (payment info, personal details)

- Implement access control mechanisms for sensitive user data

- Regularly audit security measures to prevent data breaches

5. Customer Feedback and Analytics:

- Task 5.1: Customer Feedback System

- Build a system to collect and analyze customer reviews and ratings

- Implement post-purchase feedback mechanisms to improve product and service quality

- Set up automated emails for customers to provide feedback after using the platform

- Task 5.2: Data Analytics and Reporting

- Set up tools to analyze customer feedback data and generate reports

- Build dashboards to track trends in user behavior, preferences, and sales performance

- Develop a system for interpreting data to recommend future product features

Estimating Duration for Major WBS Components:

The estimated duration for the major WBS components is as follows (unit in months):

1. Platform Development:

- Task 1.1: Car Showcase Module - 1.5 months

- Task 1.2: Sales Functionality - 2 months

- Task 1.3: User Account Management - 1 month

- Task 1.4: Vehicle Inventory Management - 1.5 months

Total for Platform Development: 6 months

2. Charging Station Finder:

- Task 2.1: Charging Station Database Integration - 1.5 months

- Task 2.2: Route Recommendation System - 2.5 months

Total for Charging Station Finder: 4 months

3. AI/ML Integration:

- Task 3.1: AI System for Self-Driving (Not implemented initially) - Defer

- Task 3.2: Data Collection and Analytics for AI - 2 months

Total for AI/ML Integration: 2 months (if implemented)

4. Security and Data Protection:

- Task 4.1: Secure Payment Gateway Integration - 1 month

- Task 4.2: Data Security and Encryption - 1.5 months

Total for Security: 2.5 months

5. Customer Feedback and Analytics:

- Task 5.1: Customer Feedback System - 1 month

- Task 5.2: Data Analytics and Reporting - 2 months

Total for Customer Feedback and Analytics: 3 months

1.3 Estimated Total Project Duration:

Summing up the major components, we have:

Platform Development: 6 months

Charging Station Finder: 4 months

AI/ML Integration: 2 months (if implemented)

Security: 2.5 months

Customer Feedback and Analytics: 3 months

Total Duration: 19 months (Assuming AI/ML features are deferred)

- Delphi Wideband Estimation (DWE):

The Delphi Wideband Estimation (DWE) technique is a group-based method used to estimate the duration or effort required for a project task. It involves a group of experts providing their independent estimates, followed by discussions, and then refining the estimates iteratively until a consensus is reached.

Steps in the Delphi Wideband Estimation (DWE) Process:

1. Assemble Tasks:

Activity:

- The project manager assembles a team of experts who are familiar with the project's scope and requirements. In this case, we have an estimation team of five members (experts in various domains such as software development, AI, security, and user experience).

Tasks:

- Define the tasks clearly, e.g., “Develop car showcasing module,” “Integrate secure payment gateway,” “Create AI system for self-driving cars,” etc.

- Break down the overall project into smaller, more manageable tasks (Work Breakdown Structure - WBS) to be estimated.

2. Initial Estimation by Experts:

Activity:

- Each member of the estimation team provides their independent estimate for the duration or effort required for each task.

- The estimates can be provided in terms of days, weeks, or months depending on the complexity of the task.

- These are typically provided anonymously to avoid bias from groupthink or influential members.

For example:

- Task 1 (Develop car showcase module): Expert 1 estimates 2 weeks, Expert 2 estimates 3 weeks, and so on.

3. Group Discussion and Clarification:

Activity:

- Once the initial estimates are gathered, the project manager or moderator arranges a group discussion to review the estimates and clarify any ambiguities.

- Each expert explains the rationale behind their estimate.

- The purpose of the discussion is to uncover any misunderstandings about the scope, assumptions, or constraints that might have influenced the estimates.

For example:

- Expert 1 may explain that their estimate is based on the complexity of the user interface required for the car showcase.

- Expert 2 might suggest that additional features for payment integration may make the task more complex, requiring more time.

4. Re-estimation and Refinement:

Activity:

- After the discussion, the experts are asked to revise their estimates based on the insights shared during the group discussion.

- This process allows the team to refine the estimates by considering all perspectives and gaining a deeper understanding of the tasks involved.

For example:

- After discussing potential difficulties, Expert 1 revises their estimate to 3 weeks for the car showcase module, and Expert 2 revises to 4 weeks, and so on.

5. Final Estimation and Consensus:

Activity:

- The group revises the estimates one more time based on the discussion and any additional information shared.

- A consensus is reached on the final estimates, which will then be used for scheduling and resource planning.

For example:

- The final agreed-upon estimate for the car showcase module might be 3 weeks.

Estimation Form and Tentative Convergence Chart:

The estimation form should capture the initial estimates, final estimates, and any necessary comments or justifications provided by the experts.

| Task | Expert 1 Estimate | Expert 2 Estimate | Expert 3 Estimate | Expert 4 Estimate | Expert 5 Estimate | Final Estimate | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Develop Car Showcase Module | 2 weeks | 3 weeks | 2.5 weeks | 3 weeks | 3 weeks | 3 weeks | Difficulty in UI design and integration |
| Integrate Secure Payment Gateway | 1.5 weeks | 1 week | 1.5 weeks | 2 weeks | 1.5 weeks | 1.5 weeks | Complexity of third-party integration |
| AI System for Self-Driving (Future) | Deferred | Deferred | Deferred | Deferred | Deferred | Deferred | Feature deferred to future phase |
| Real-Time Exam Monitoring | 3 weeks | 4 weeks | 3.5 weeks | 4 weeks | 4 weeks | 3.5 weeks | Use of AI and camera integration |

Tentative Convergence Chart:

The convergence chart tracks the progress of estimates toward a final agreement. The y-axis represents the number of days or weeks, and the x-axis represents the iteration or stage of the estimation process.

For example, after the first round, the experts’ estimates might be spread out, but after each round of discussion and re-estimation, the estimates converge towards a single value.

| Iteration | Expert 1 | Expert 2 | Expert 3 | Expert 4 | Expert 5 | Final Estimate |
| --- | --- | --- | --- | --- | --- | --- |
| 1st Round | 2 weeks | 3 weeks | 2.5 weeks | 3 weeks | 3 weeks |  |
| 2nd Round | 3 weeks | 4 weeks | 3 weeks | 3.5 weeks | 3.5 weeks |  |
| Final | 3 weeks | 4 weeks | 3.5 weeks | 3.5 weeks | 3 weeks | 3 weeks |

This convergence chart helps visualize how the estimates stabilize over time as experts discuss and refine their initial estimates.

The Delphi Wideband Estimation (DWE) technique involves iterative rounds of independent estimation, group discussion, and refinement of estimates. By utilizing expert opinions and fostering collaboration, the DWE technique helps ensure more accurate and realistic project estimates. This technique is particularly useful in complex projects like the Electric Car Brand Software, where various stakeholders with different expertise need to provide insights and agree on the timeline for task completion.

- Risk Plan Sheet:

This document presents the risk plan for the EV software scenario provided. The plan uses a 1 to 5 scale for Probability and Impact, calculating Risk Priority as Probability multiplied by Impact. The risks are identified based on the scenario, requirements and constraints.

| Risk ID | Risk Description | Probability (1–5) | Impact (1–5) | Risk Priority | Mitigation Strategy | Responsible Person |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Scope creep from continuous feature requests and expansion beyond cars | 4 | 5 | 20 | Establish a formal change-control board; enforce MoSCoW prioritization; timebox changes into future releases; maintain a rolling 3-sprint roadmap with capacity buffers; ensure updated SoW before starting any major scope addition | Project Manager |
| R2 | Skill gap in data science/AI required for feedback analytics and potential ML features | 3 | 4 | 12 | Hire or contract a Data Scientist in Month 1–3; upskill devs with targeted training; design data pipelines now even if ML models come later; keep vendor/partner shortlist ready | Engineering Manager |
| R3 | Cybersecurity/OTA vulnerability leading to data breach or vehicle control risk | 3 | 5 | 15 | Security-by-design reviews for each module; threat modeling; secure OTA update pipeline with code signing; periodic penetration tests; strict secrets management; incident runbooks and response drills | Security Lead |
| R4 | External data dependency for maps and charging stations causes outages or bad routes | 3 | 4 | 12 | Dual-source providers where possible; cache critical POIs; graceful degradation in app; SLO monitoring and alerts; contract SLAs with providers | Platform Lead |
| R5 | Regulatory change for EV software data privacy, safety, or telematics | 2 | 4 | 8 | Track upcoming rules with quarterly reviews; implement privacy-by-default; feature flags to toggle or regionalize behavior; legal review before region launches | Compliance Officer |
| R6 | Integration complexity across Platform, EV, Security, AI/ML slows delivery | 3 | 4 | 12 | Define versioned service contracts; CI with contract tests; a weekly integration build; a ‘system architect’ gate before merging cross-module changes | System Architect |
| R7 | Schedule overrun due to underestimated effort across modules | 3 | 4 | 12 | Use Wideband Delphi estimates; add 15–20% contingency to the critical path; track SPI/CPI weekly; cut or defer lower-priority features early | Project Manager |
| R8 | Cloud cost overrun from telemetry, maps, and analytics | 3 | 3 | 9 | Cost budgets per environment; autoscali ng guardrails; storage lifecycle rules; monthly FinOps review; load testing before scale-up | DevOps Lead |
| R9 | Quality regressions when adding frequent features to ‘stay competitive’ | 3 | 4 | 12 | CI with unit/integration/e2e tests; release trains; feature flags and canary releases; bug SLAs and DOR/DoD checklists | QA Lead |
| R10 | Stakeholder availability risk delaying sign-offs in module reviews | 2 | 3 | 6 | Publish review calendar for the whole semester; name delegates with decision power; asynchronous sign-off windows with clear acceptance criteria | Product Owner |