# Project Management Mid Solution (Spring-26)

# Question1. Software Engineering Methodology:

Recommended Methodology: Agile (Scrum)

- Complex Features and Integration: The platform needs integration with national ID databases and financial services. SCRUM’s iterative process allows continuous adaptation and integration of these complex systems.

- Evolving Stakeholder Needs: SCRUM's flexibility supports evolving requirements as new stakeholders (government, financial institutions, local authorities) provide feedback throughout the project.

- Phased Development Approach: Starting with basic functionalities (registration, payments) and expanding to advanced features (AI, fraud detection). SCRUM allows for incremental development with each sprint focusing on key features.

- Rural Internet and Offline Functionality: SCRUM enables focused development of offline features for rural areas in specific sprints, addressing internet access issues while ensuring core functionalities are tested early.

- Security and Data Protection: SCRUM allows early implementation of security measures (encryption, authentication) in each sprint, ensuring robust data protection for sensitive financial and personal data.

- Collaboration and Cross-functional Teams: The project requires collaboration among government agencies, developers, and AI experts. SCRUM fosters teamwork through regular meetings and continuous stakeholder feedback, ensuring all parties are aligned.

- Frequent Testing and Adjustments: SCRUM’s short cycles allow regular testing, bug fixing, and real-time adjustments to ensure the platform meets user needs, especially for non-tech-savvy users.

- Product Backlog:

  - A prioritized list of features, requirements, and fixes needed for the project.

  - Continuously updated by the Product Owner based on feedback and evolving needs.

  - Example items: Family registration, AI eligibility checks, mobile app, security features, offline capability, and fraud detection.

- Daily Scrum:

  - A 15-minute daily meeting for the team to synchronize and plan.

  - Each member answers:

    - What did I do yesterday?

    - What will I do today?

    - Any blockers?

  - Helps identify issues early, adjust priorities, and ensure alignment.

# Question 2. Vision and Scope Document:

A Project Plan is a comprehensive document that outlines the approach, timeline, resources, and activities required to complete a project successfully. It serves as a roadmap for project execution, tracking, and monitoring. It typically includes the following elements:

- Project Scope: Defines what will and won’t be included in the project.

- Objectives: Describes the goals of the project.

- Timeline: Outlines milestones, deadlines, and project phases.

- Budget: Estimates costs, resources, and financial allocation.

- Risk Management: Identifies potential risks and mitigation strategies.

- Resource Allocation: Details the human, technical, and financial resources.

- Communication Plan: Explains how information will be shared among stakeholders.

- Quality Assurance: Specifies how the quality of the product will be ensured.

Vision Document:
The Digital Family Card–Based Smart Welfare Distribution Platform aims to ensure that financial aid and subsidies are distributed fairly and transparently to low-income and vulnerable families across Bangladesh. The platform will create a centralized system for managing household data, integrating national ID systems and financial services, and providing benefits directly to citizens through a digital card.

Scope Document:

In-Scope:

- Development of a digital family registration system.

- Integration with national ID databases and financial institutions for subsidy distribution.

- AI-based eligibility checking for determining welfare eligibility.

- Automatic monthly payments through mobile and banking platforms.

- Mobile application and SMS services for citizens to check payments and updates.

- Security features such as encryption, authentication, and fraud detection.

- Data analytics dashboards for government officials to track and monitor distribution trends.

Out-of-Scope:

- International integrations beyond Bangladesh’s national systems.

- Features unrelated to welfare distribution (e.g., non-governmental services).

Key Stakeholders:

- Government officials (for monitoring and distribution tracking)

- Developers and AI experts (for platform development)

- Financial institutions and mobile services (for payment handling)

- Local authorities (for registration and verification)

- Citizens (end-users)

Milestones:

- Initial development of registration system and payments (Phase 1)

- Integration of AI eligibility checking and fraud detection (Phase 2)

- Full integration with financial services and analytics dashboard (Phase 3)

Assumptions:

- The national ID system will be fully functional and accessible for integration.

- Mobile financial services are widely used and available across Bangladesh.

Constraints:

- Limited internet connectivity in rural areas.

- Security concerns related to handling sensitive personal and financial data.

# Question 3. Work Breakdown Structure (WBS):

Rules for Generating a WBS:

  100% Rule: The WBS must include all work required—nothing extra, nothing missing.

  Decomposition: Break work into smaller, manageable components until they are easy to estimate and assign.

  No Overlap: Each task should be unique (no duplication of work).

  Deliverable-Oriented: Focus on outcomes (features/modules), not just activities.

  Manageable Size: Each lowest-level task (work package) should be small enough to estimate time and cost clearly.

  Hierarchical Structure: Maintain a clear parent-child relationship.

| ### 1. Project: Digital Family Card Smart Welfare System #### 1.1 Project Initiation & Planning - 1.1.1 Requirement Gathering - 1.1.2 Stakeholder Analysis - 1.1.3 Feasibility Study - 1.1.4 Project Plan Preparation #### 1.2 System Design - 1.2.1 Architecture Design - 1.2.2 Database Design - 1.2.3 UI/UX Design (Mobile + Web) - 1.2.4 Security Design #### 1.3 Core System Development - 1.3.1 Digital Family Registration Module - 1.3.2 National ID Integration - 1.3.3 AI-Based Eligibility Checking - 1.3.4 Payment Processing Integration (MFS & Banks) - 1.3.5 QR/NFC Smart Card System | #### 1.4 Supporting Features - 1.4.1 Dashboard for Government Officials - 1.4.2 Mobile App Development - 1.4.3 SMS Notification System - 1.4.4 Offline/Low Internet Support #### 1.5 Testing & Quality Assurance - 1.5.1 Unit Testing - 1.5.2 Integration Testing - 1.5.3 Security Testing - 1.5.4 User Acceptance Testing (UAT) #### 1.6 Deployment & Integration - 1.6.1 Deployment Setup - 1.6.2 Integration with External Systems - 1.6.3 Data Migration #### 1.7 Training & Support - 1.7.1 Training for Local Officials - 1.7.2 User Documentation - 1.7.3 Maintenance & Support |
| --- | --- |

# Question 4. Delphi Wideband Estimation (DWE):

Kickoff Meeting Activities for Delphi Wideband Estimation (DWE):

In the Wideband Delphi kickoff meeting, the moderator presents the project scope, discusses assumptions and constraints with the team, and helps the team brainstorm a high-level work breakdown structure (WBS) and decide on estimation units. The primary goal is to get the estimation team on the same page regarding the project and the estimation process, ensuring everyone is ready to proceed to the individual preparation phase.

| Task Name | Description | Estimated Duration by Team Member 1 | Estimated Duration by Team Member 2 | Estimated Duration by Team Member 3 | Estimated Duration by Team Member 4 | Estimated Duration by Team Member 5 | Average Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Initiation & Planning | Requirement gathering, feasibility study, project planning | 2 months | 2 months | 3 months | 2 months | 2 months | 2.2 months |
| System Design | Architecture, database, UI/UX, and security design | 3 months | 3 months | 4 months | 3 months | 3 months | 3.2 months |
| Core System Development | Registration, NID integration, AI eligibility, payment system, smart card | 7 months | 6 months | 8 months | 5 months | 7 months | 6.6 months ≈ 6 months |
| Supporting Features | Dashboard, mobile app, SMS system, offline support | 3 months | 4 months | 3 months | 3 months | 3 months | 3.2 months |
| Testing & QA | Unit, integration, security, and UAT testing | 4 months | 3 months | 4 months | 5 months | 3 months | 3.8 months ≈ 3 months |
| Deployment & Integration | System deployment, external integration, data migration | 2 months | 2 months | 3 months | 2 months | 2 months | 2.2 months |
| Training & Maintenance | Training, documentation, and ongoing support | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing |

Tentative Convergence Chart

| Round | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Range (Min–Max) | Average |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Round 1 | 7 months | 6 months | 8 months | 5 months | 7 months | 5 – 8 | 6.6 months |
| Round 2 | 6 months | 6 months | 7 months | 6 months | 6 months | 6 – 7 | 6.2 months |
| Round 3 | 6 months | 6 months | 6 months | 6 months | 6 months | 6 – 6 | 6.0 months |

# Question 5. Risk Plan Sheet:

RMMM stands for:

- Risk Mitigation → Steps taken to reduce the probability of a risk occurring

- Risk Monitoring → Continuously tracking identified risks and detecting new ones

- Risk Management → Planning actions to handle risks if they occur

| Risk ID | Risk Description | Probability | Impact | Risk Exposure | Mitigation Plan | Monitoring Strategy | Management Plan |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Data security breach (sensitive personal & financial data) | High | High | Very High | Use strong encryption, multi-factor authentication, secure APIs | Regular security audits, intrusion detection systems | Immediate isolation, fix vulnerability, notify stakeholders |
| R2 | Integration failure with National ID & financial systems | Medium | High | High | Early integration testing, use standardized APIs | Continuous integration monitoring, API testing | Assign expert team, fallback manual verification |
| R3 | Poor internet connectivity in rural areas | High | Medium | High | Develop offline functionality, SMS-based services | Monitor system usage and failure rates in rural regions | Provide offline sync, local data storage solutions |
| R4 | Incorrect AI-based eligibility decisions | Medium | High | High | Train AI with quality data, validate models | Monitor AI outputs, periodic accuracy checks | Manual override system, human review process |