# Project Management Mid Solution (Summer-25)

# Question1. Software Engineering Methodology:

Recommended Methodology: Agile (Scrum)
Why Scrum:

- Breaks solution into smaller modules with reviews each sprint.

- Prioritizes client collaboration and evolving requirements.

- Delivers working software early (e.g., inventory, mobile app first).

- Manages risks with frequent testing and feedback.

- Scales well for multiple teams and regional growth.

- Encourages cross-functional teamwork.

Drawbacks of XP:

- Needs constant customer involvement.

- Not ideal for large teams or scalable projects.

- Too code-focused, light on documentation.

When XP fits best:

- Small to medium projects with rapidly changing needs.

- Daily customer input and quick code feedback are essential.

- Teams are co-located and ready for pair programming & strict testing.

# Question 2. Vision and Scope Document:

Vision:
To develop a Smart Retail System that integrates in-store and online shopping, improves inventory management, enhances customer engagement, and provides a seamless shopping experience.

Scope:

- In Scope:

  - Real-time inventory management across stores.

  - Product catalog integration.

  - Mobile app (browse, purchase, delivery options).

  - Customer engagement (discounts, suggestions).

  - Payment gateway integration.

- Out of Scope (for now):

  - AI-based demand prediction.

  - Advanced analytics & ML features.

- Constraints:

  - Integration with existing infrastructure.

  - Security of customer data & transactions.

- Stakeholders: Client, Project Manager, Dev Team, Data Scientist (future), Cybersecurity Expert.

# Question 3. Work Breakdown Structure (WBS):

Rules for Generating a WBS:

- Decomposition: Break the project into smaller components for easy management.

- Hierarchical Structure: Organize tasks in levels, from major deliverables to detailed tasks.

- Clear Deliverables: Each component must have a defined output.

- Mutually Exclusive: Avoid overlapping tasks.

- Consistent Numbering: Use a clear numbering system for hierarchy.

- Clarity: Tasks should be easily understood.

- Activity Breakdown: If necessary, break down tasks further for better estimation.

Estimating Duration for Two Major WBS Components:

Component 1: Inventory Management System (Duration Estimate: 6 months)

- Requirements Gathering: 1 month

  - Engage with stakeholders, understand needs, and gather all system requirements.

- System Design: 1 month

  - Design the architecture of the system, including databases, workflows, and user interfaces.

- Development: 2 months

  - Develop the core inventory system functionalities such as stock tracking, updates, and synchronization.

- Integration with E-commerce Platform: 1 month

  - Ensure that the inventory system communicates with the e-commerce platform in real-time.

- Testing and QA: 1 month

  - Perform unit and system integration tests to verify functionality and bug-free performance.

- Deployment: 1 month

  - Deploy the system into the production environment after successful testing.

Component 2: Mobile App Development (Duration Estimate: 7 months)

- UI/UX Design: 1 month

  - Design the interface of the app, ensuring it's user-friendly and meets client expectations.

- Frontend Development: 2 months

  - Develop the client-side of the app, ensuring that customers can interact with the product catalog and make purchases.

- Backend Development: 2 months

  - Build the server-side infrastructure, ensuring smooth data synchronization and integration with the inventory and payment systems.

- Integration with Payment Gateway & Inventory: 1 month

  - Integrate a third-party payment gateway and ensure the app syncs with the real-time inventory.

- Testing: 1 month

  - Perform functional, integration, and security testing of the app.

- Deployment: 1 month

  - Deploy the app to the app stores and handle post-launch support.

# Question 4. Delphi Wideband Estimation (DWE):

Kickoff Meeting Activities for Delphi Wideband Estimation (DWE):

In the Wideband Delphi kickoff meeting, the moderator presents the project scope, discusses assumptions and constraints with the team, and helps the team brainstorm a high-level work breakdown structure (WBS) and decide on estimation units. The primary goal is to get the estimation team on the same page regarding the project and the estimation process, ensuring everyone is ready to proceed to the individual preparation phase.

Sample Individual Estimation form for Component 1 (Inventory Management System):

| Task Name | Est. (Months) | Delta 1 | Delta 2 | Delta 3 | Total | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements Gathering | 1.0 | +0.5 | -0.2 | +0.3 | 1.6 | Stakeholder meetings needed |
| System Design | 1.0 | +0.4 | +0.1 | -0.3 | 1.2 | Complex workflows |
| Development | 2.0 | +1.0 | -0.5 | +0.5 | 2.5 | Includes UI and backend work |
| Integration with E-commerce | 1.0 | +0.2 | +0.1 | -0.1 | 1.2 | API for real-time sync |
| Testing and QA | 1.0 | +0.3 | -0.1 | +0.2 | 1.4 | Stress tests required |
| Deployment | 1.0 | +0.1 | -0.1 |  | 1.1 | Production environment setup |
| Grand Total | 6.0 |  |  |  | 9.0 |  |

Explanation:

- Est. (Months) column total = 1 + 1 + 2 + 1 + 1 + 1 = 6 months

- Total column total = 1.6 + 1.2 + 2.5 + 1.2 + 1.4 + 1.1 = 9.0 months (including delta adjustments)

Tentative Convergence Chart

| Task Name | Round 1 | Round 2 | Round 3 | Final Estimate (Total) |
| --- | --- | --- | --- | --- |
| Requirements Gathering | 1.0 | 1.3 | 1.5 | 1.6 |
| System Design | 1.0 | 1.1 | 1.2 | 1.2 |
| Development | 2.0 | 2.3 | 2.4 | 2.5 |
| Integration with E-commerce | 1.0 | 1.1 | 1.2 | 1.2 |
| Testing and QA | 1.0 | 1.2 | 1.3 | 1.4 |
| Deployment | 1.0 | 1.0 | 1.1 | 1.1 |

# Question 5. Risk Plan Sheet:

| Risk ID | Risk Description | Impact | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Integration Issues with Existing Systems | High | Medium | - Engage early with client’s IT department to understand legacy systems.- Involve integration experts from the beginning. |
| R2 | Security Breaches in Mobile App or Payment System | High | High | - Hire a cybersecurity expert to design secure systems.- Implement encryption, multi-factor authentication, and regular security audits. |
| R3 | Scope Creep and Changing Client Requirements | Medium | High | - Establish clear project milestones.- Implement an agile process for flexible scope management and frequent client feedback. |