# Final Term Exam (Fall 2025): Research Grant and Publication Management System

PMG 4101 Project Management | Solutions to Q1-Q5 (Q6 skipped as instructed)

## Q1. Project Type and COCOMO [7]

i. Project type: Semidetached

- Team: mixed experience (13 experienced engineers + 27 fresh graduates), not all expert and not all novice.

- Size and complexity: medium-large; multi-level approval workflows, role-based access, audit logging, versioning, integration with indexing services, finance and HR systems.

- Requirements: mix of rigid (security, funding-agency and accreditation compliance) and flexible (UI, report formats) requirements.

- Constraints: no tight hardware or real-time constraints, so not Embedded. Too large and complex for a small, familiar-environment team, so not Organic.

ii. COCOMO parameters

- FP = 1250, LOC/FP = 40, so LOC = 50,000 and KLOC = 50

- Constants (Semidetached): a = 3.0, b = 1.12, c = 2.5, d = 0.35

- Effort E = 3.0 x (50)^1.12 = 3.0 x 79.95 = 239.9 person-months

- Duration D = 2.5 x (239.9)^0.35 = 2.5 x 6.81 = 17.0 months

- Average staff = E / D = 239.9 / 17.0 = about 14 persons

- Productivity = 50,000 / 239.9 = about 208 LOC/PM (5.2 FP/PM)

- Budget (assuming average cost BDT 60,000 per person-month) = 239.9 x 60,000 = about BDT 1.44 crore

## Q2. Change Control [7]

i. Concept and importance Change control is the formal process of requesting, evaluating, approving, implementing and tracking changes to baselined project items (requirements, design, code, documents).

Importance: prevents scope creep, protects baselines, shows cost/schedule/risk impact before work starts, keeps changes traceable, and keeps stakeholders (university management, funding agencies) in agreement.

ii. Role of the Tester in the CCB

- Represents quality and the product's stability in decisions.

- Assesses testability and test effort of each change request.

- Plans regression tests so existing features (e.g. approval workflow, budget tracking) are not broken.

- Verifies the implemented change and reports results to the CCB.

- Keeps traceability between change requests and test cases.

iii. Steps

( Not the only process to answer the Basic Course of Event and Alternative Path. You can keep whatever mentioned in the slide as an answer and mention actual changes might occur at first. Like the way mentioned in the class)

Basic course of events

- A Change Request (CR) is submitted (e.g. a new funding-agency report format).

- CR is logged with a unique ID by the configuration manager.

- Impact analysis on scope, cost, schedule, risk and quality.

- CCB approves, rejects or defers the CR.

- If approved, update plan and baselines, and assign the work.

- Developers implement the change under version control.

- Tester verifies it and runs regression tests.

- CCB/PM approves the release; update documents and version.

- Close the CR and inform stakeholders.

Alternate steps

- A1: CR incomplete: return to requester.

- A2: Rejected: record reason, notify requester, close.

- A3: Deferred: move to a later release.

- A4: Emergency change (e.g. security vulnerability): fast-track by CCB chair, ratify later.

- A5: Tests fail: back to implementation, or roll back.

- A6: Impact beyond PM authority: escalate to university management.

## Q3. Dependencies and Gantt Chart [10]

i. Dependencies among activities A dependency is a relationship that decides the order in which activities can start or finish. In software building, for example, design must finish before coding, and coding before testing.

- Finish-to-Start (FS): B starts after A finishes (design, then coding). Most common.

- Start-to-Start (SS): B starts when A starts (documentation alongside coding).

- Finish-to-Finish (FF): B finishes when A finishes (testing ends with coding).

- Start-to-Finish (SF): rare (old system stops when the new one starts).

- Also classified as mandatory (logical), discretionary, external (e.g. HR/finance system access) or internal.

Dependencies decide the critical path, so a delay on it delays the whole project.

ii. Gantt chart

| ID | Task | Duration (wks) | Depends on | Weeks |
| --- | --- | --- | --- | --- |
| A | Requirements and SRS | 4 | none | 1-4 |
| B | Architecture, security and DB design | 5 | A | 5-9 |
| C | Core platform: RBAC, user management, DB | 8 | B | 10-17 |
| D | Proposal, budget and ethical clearance forms | 10 | C | 18-27 |
| E | Multi-level approval and review workflow | 10 | C | 18-27 |
| G | Publication repository, versioning, audit log | 10 | C | 18-27 |
| F | Finance module (disbursement, expenses, balances) | 8 | D, E | 28-35 |
| J | Data migration | 6 | D, E | 28-33 |
| H | Reports and analytics | 6 | F, G | 36-41 |
| I | Integration (indexing services, finance, HR) | 8 | F, G | 36-43 |
| K | Security hardening and backup | 4 | I | 44-47 |
| L | System, performance and security testing | 8 | H, J, K | 48-55 |
| M | UAT and user training | 6 | L | 56-61 |
| N | Deployment and go-live support | 4 | M | 62-65 |
| - | Holiday/risk buffer | 9 | N | 66-74 |

(1 char = 2 weeks)
A Requirements    ##
B Design + DB       ###
C Core + RBAC         ####
D Proposal forms          #####
E Approval flow           #####
G Publication repo        #####
F Finance module               ####
J Data migration               ###
H Reports                          ###
I Integrations                     ####
K Security/backup                      ##
L Testing                                #### 
M UAT + training                             ###
N Go-live                                       ##
Buffer                                            .....

Critical path: A, B, C, D/E, F, I, K, L, M, N (65 weeks + 9-week buffer = 74 weeks, about 17 months, matching COCOMO).

(Not required to use “#” for gantt chart. You can use lines as well. Also critical path, milestone, and Assumptions can be ignored if it is not mentioned in the question. )

Milestones: design sign-off (week 9), core platform demo (week 17), workflow and forms demo (week 27), compliance review before testing (week 47), go-live (week 65).

Assumptions:

- Fri-Sat weekly holidays; 5-day work week.

- Government holidays (Eid-ul-Fitr, Eid-ul-Adha, Independence Day, Victory Day, Language Day, Pohela Boishakh, Durga Puja) covered by buffer.

- Peak submission and reporting periods are avoided for go-live.

- Learning curve of 27 fresh graduates and some rework.

- Finance/HR system access and indexing-service APIs are available on time.

## Q4. Review Method [6]

Justification

- Organization structure: 13 experienced engineers (architecture, security, integration) and 27 fresh graduates (UI, testing, migration). A formal role-based review lets seniors control quality and mentor the freshers.

- Aspect of task: Complex (multi-level workflows, integrations), long (about 17 months) and important (sensitive financial and IP data, accreditation and funding-agency reporting). Defects are costly, so strict review is needed.

- Time: Long schedule with milestone-based compliance reviews, so time exists for planned reviews at each milestone.

Appropriate review: Formal Inspection (not desk check, which is informal and individual, nor walkthrough, which is less rigorous).  (You can choose another review technique as well)

Activities

- Planning: moderator selects inspectors and schedules.

- Overview: author presents the artifact.

- Preparation: inspectors review individually using checklists.

- Inspection meeting: reader walks through, recorder logs defects (no fixing in the meeting).

- Rework: author fixes the defects.

- Follow-up: moderator verifies the fixes and closes the inspection.

## Q5. DMAIC vs DMADV [5]

Current state: Grants, publications and compliance are handled with spreadsheets, emails and fragmented systems. The process is manual, inconsistent and has no reliable baseline data.

Target state: A new, centralized, automated system with workflows, security and reporting.

Choice: DMADV (Define, Measure, Analyze, Design, Verify)

Reasons

- New design, not a tweak: DMADV is for designing a new product or process. DMAIC improves an existing, stable process, but the current process is fragmented and has no baseline to improve.

- Customer needs first: Measure turns needs into CTQs (deadline accuracy, data consistency, security, thousands of concurrent users); Analyze compares design options.

- Design and verify: Design covers architecture, workflows and RBAC; Verify uses pilot, UAT and performance testing before go-live, which fits milestone-based compliance reviews.

- Risk: Building it right the first time is important for sensitive financial and IP data.

After go-live, DMAIC can be used for continuous improvement of the running system (e.g. cutting approval time).