# Final Term Exam (Spring 2025): Import-Export Digital System

PMG 4101 Project Management | Solutions to Q1-Q6 (Q7 skipped as instructed)

## Q1. CT, VAF and FP [8]

UI features are simple, so EI/EO/EQ use the Simple weight. Data files are very complex, so ILF/EIF use the Complex weight.

| Type | Items identified | Count | Weight | Total |
| --- | --- | --- | --- | --- |
| EI | Account/profile, permit application, permit approval, payment, customs entry, SWISS transfer | 6 | 3 | 18 |
| EO | Product-performance review report, currency-exchange dashboard, transaction trace report | 3 | 4 | 12 |
| EQ | Application progress tracking, order tracking, official's party-information lookup | 3 | 3 | 9 |
| ILF | User/profile, permit-application, order/customs, payment databases | 4 | 15 | 60 |
| EIF | SWISS network, exchange-rate source | 2 | 10 | 20 |

CT (Count Total) = 18 + 12 + 9 + 60 + 20 = 119

TDI (scale: moderate = 2, average = 3, significant = 4, essential = 5)

- F1-F7 significant: 7 x 4 = 28

- F8, F9 essential: 2 x 5 = 10

- F12, F14 moderate: 2 x 2 = 4

- F10, F11, F13 average: 3 x 3 = 9

- TDI = 51

VAF = 0.65 + 0.01 x 51 = 1.16

FP = CT x VAF = 119 x 1.16 = 138.04 (about 138)

## Q2. COCOMO [5]

- LOC = 138.04 x 128 = 17,669, so KLOC = 17.67

- Type: Semidetached. Mixed team (10 experienced + 15 freshers), medium-large size, mix of rigid (government, payment) and flexible requirements, no hardware constraints.

- Constants: a = 3.0, b = 1.12, c = 2.5, d = 0.35

- Effort E = 3.0 x (17.67)^1.12 = 3.0 x 24.94 = 74.8 person-months

- Duration D = 2.5 x (74.8)^0.35 = 2.5 x 4.53 = 11.3 months

- Average staff = E / D = 74.8 / 11.3 = about 7 persons

- Productivity = 17,669 / 74.8 = about 236 LOC/PM (1.85 FP/PM)

- Budget (assuming average cost BDT 60,000 per person-month) = 74.8 x 60,000 = about BDT 44.9 lakh

## Q3. Change Control [7]

Concept: Change control is the formal process of requesting, evaluating, approving, implementing and tracking changes to baselined items (requirements, design, code, documents).

Purpose: Prevent scope creep, protect baseline integrity, assess cost/schedule/risk impact before acting, and keep every change traceable.

( Not the only process to answer the Basic Course of Event and Alternative Path. You can keep whatever mentioned in the slide as an answer and mention actual changes might occur at first. Like the way mentioned in the class)

Basic course of events

- A Change Request (CR) is raised, e.g. government asks to add SWISS.

- Configuration manager logs the CR with a unique ID.

- Impact analysis: scope, cost, schedule, risk, quality.

- Change Control Board (CCB) reviews and decides: approve, reject or defer.

- If approved, update plan and baselines, and assign the work.

- Developers implement the change in version control.

- Testers verify the change and run regression tests.

- CCB/PM approves release; update documents and version.

- Close the CR and inform stakeholders.

Alternate steps

- A1: CR unclear or incomplete: return to requester for clarification.

- A2: Rejected: record reason, notify requester, close.

- A3: Deferred: move to backlog for a later release.

- A4: Emergency change (e.g. payment bug): fast-track approval by PM/CCB chair, ratify later.

- A5: Tests fail: return to step 6, or roll back to the previous baseline.

- A6: Impact exceeds PM authority (budget/deadline): escalate to the government sponsor.

## Q4. Gantt Chart [5]

| ID | Task | Duration (wks) | Depends on | Weeks |
| --- | --- | --- | --- | --- |
| A | Requirements and SRS | 4 | none | 1-4 |
| B | Architecture and design | 4 | A | 5-8 |
| C | Database implementation | 4 | B | 9-12 |
| D | Exporter/importer account web-app | 6 | B | 9-14 |
| E | Permit application portal | 6 | C | 13-18 |
| F | Government officials portal | 6 | E | 19-24 |
| G | Application progress tracking | 3 | E | 19-21 |
| H | Payment gateway + SWISS | 8 | D | 15-22 |
| I | Order tracking + customs tracking | 6 | F, G | 25-30 |
| J | Review system + exchange-rate dashboard | 5 | H, I | 31-35 |
| K | Integration and system testing | 6 | J | 36-41 |
| L | UAT, training, deployment | 4 | K | 42-45 |
| - | Holiday/risk buffer | 4 | L | 46-49 |

(1 char = 1 week)
A Requirements    ####
B Design              ####
C Database                ####
D Account web-app         ######
E Permit portal               ######
F Govt portal                       ######
G Progress track                    ###
H Payment+SWISS                 ########
I Orders/customs                        ######
J Review+dashboard                            #####
K Integration/test                                 ######
L UAT & deploy                                           ####
Holiday buffer                                               ....

Critical path: A, B, C, E, F, I, J, K, L (45 weeks + 4-week buffer = 49 weeks, about 11.3 months, matching COCOMO).

(Not required to use “#” for gantt chart. You can use lines as well. Also critical path, milestone, and Assumptions can be ignored if it is not mentioned in the question. )

Assumptions:

- Fri-Sat weekly holidays; 5-day work week.

- Government holidays: Eid-ul-Fitr, Eid-ul-Adha, Independence Day, Victory Day, Language Day, Pohela Boishakh, Durga Puja.

- Learning curve of 15 freshers; some rework.

- Government approvals and feedback arrive on time.

- Core team stays stable (no major attrition).

## Q5. Review Method [5]

Justification

- Organization structure: 10 experienced + 15 freshers with several teams (portals, payment, database). A formal, role-based review lets seniors check and mentor freshers.

- Aspect of task: Complex (SWISS, payment, large databases), long (about 11 months) and highly important (national trade, money, legal compliance). Defects here are costly, so rigorous review is needed.

- Time: Enough schedule for planned reviews at each phase; fixing defects early is cheaper than fixing them late.

Appropriate review: Formal Inspection (not desk check, which is informal and individual, nor walkthrough, which is author-led and less rigorous). (You can choose another review technique as well)

Activities

- Planning: moderator selects inspectors and schedules.

- Overview: author explains the artifact.

- Preparation: inspectors review individually using checklists.

- Inspection meeting: reader walks through, recorder logs defects (no fixing in the meeting).

- Rework: author fixes the defects.

- Follow-up: moderator verifies fixes and closes the inspection.

## Q6. KPAs and CMMI Level III [5]

KPA (Key Process Area): A cluster of related practices that, performed together, achieve goals important for process capability at a maturity level.

Current level: Level 2 (Managed). The organization has built management systems before, so project-level practices exist (planning, tracking, requirements management, configuration management, QA). But processes are project-specific, not standardized across the organization.

Target level: Level 3 (Defined).

|  | Level 2 (current) | Level 3 (target) |
| --- | --- | --- |
| Process | Managed per project | Standard organization-wide, tailored per project |
| Approach | Reactive | Proactive |
| Documentation | Project-level | Organization process assets |

Guidelines to reach Level 3 (compliance / rubrics)

- Organizational Process Definition and Focus: create a standard process and templates; assess and improve them.

- Integrated Project Management: tailor the standard process for this project.

- Requirements Development and Technical Solution: documented requirements, design and traceability.

- Product Integration, Verification and Validation: planned integration, peer reviews/inspections, testing, UAT.

- Risk Management: identify, assess and mitigate risks (SWISS, payment, security) regularly.

- Organizational Training: train the 15 freshers in the standard process.

- Decision Analysis and Resolution: formal evaluation for key decisions (e.g. technology, vendor).