# Final Term Exam (Summer 2025): Smart Waste Management System

PMG 4101 Project Management | Solutions to Q1-Q6 (Q7 skipped as instructed)

## Q1. CT, CAF and FP [8]

UI features are average, so EI/EO/EQ use the Average weight. Data files are very complex, so ILF/EIF use the Complex weight.

| Type | Items identified | Count | Weight | Total |
| --- | --- | --- | --- | --- |
| EI | User login/registration, sensor data input, truck GPS input, manual route adjustment, privacy/consent settings | 5 | 4 | 20 |
| EO | Collection schedule notifications, route/malfunction alerts, KPI/recycling reports, optimized dispatch output | 4 | 5 | 20 |
| EQ | Bin status lookup, recycling guidelines, historical data query | 3 | 4 | 12 |
| ILF | User, bin/sensor data, historical waste data, route/truck databases | 4 | 15 | 60 |
| EIF | Traffic data source, weather data source | 2 | 10 | 20 |

CT (Count Total) = 20 + 20 + 12 + 60 + 20 = 132

Technical factors (scale: moderate = 2, average = 3, significant = 4, essential = 5)

- F1-F5 moderate: 5 x 2 = 10

- F6-F9 essential: 4 x 5 = 20

- F12, F14 significant: 2 x 4 = 8

- F10, F11, F13 average: 3 x 3 = 9

- Sum of factors = 47

CAF = 0.65 + 0.01 x 47 = 1.12

FP = CT x CAF = 132 x 1.12 = 147.84 (about 148)

## Q2. COCOMO [5]

- LOC = 147.84 x 70 = 10,349, so KLOC = 10.35

- Type: Embedded. IoT sensors and GPS hardware tightly coupled with software, real-time processing, strict reliability/security constraints, very large user base.

- Constants: a = 3.6, b = 1.20, c = 2.5, d = 0.30

- Effort E = 3.6 x (10.35)^1.20 = 3.6 x 16.52 = 59.5 person-months

- Duration D = 2.5 x (59.5)^0.30 = 2.5 x 3.41 = 8.5 months

- Average staff = E / D = 59.5 / 8.5 = about 7 persons

- Productivity = 10,349 / 59.5 = about 174 LOC/PM (2.49 FP/PM)

- Budget (assuming average cost BDT 60,000 per person-month) = 59.5 x 60,000 = about BDT 35.7 lakh

## Q3. Change Control Board and Process [6]

How the CCB is formed: The Project Manager sets up the CCB at project start through a CCB charter that defines members, authority, meeting frequency, quorum and decision rules. Members come from different stakeholder groups:

- Chair: Project Manager (final decision, escalation).

- Secretary: Configuration Manager (logs CRs, keeps records).

- Technical members: Lead developer/architect, IoT/hardware lead.

- Quality: QA/Test lead.

- Security/privacy officer (data protection compliance).

- Customer representative from the city corporations.

Purpose: Control changes to baselined items, assess impact on cost, schedule and quality, avoid scope creep, and keep traceability and stakeholder agreement.

( Not the only process to answer the Basic Course of Event and Alternative Path. You can keep whatever mentioned in the slide as an answer and mention actual changes might occur at first. Like the way mentioned in the class)

Basic course of events

- A Change Request (CR) is submitted (e.g. add a new waste type sensor).

- The configuration manager logs it with a unique ID.

- The technical team performs impact analysis (cost, time, risk, quality).

- CCB meets and approves, rejects or defers the CR.

- If approved, plans and baselines are updated and work is assigned.

- Change is implemented under version control.

- QA verifies the change and runs regression tests.

- CCB/PM approves release; documents and versions are updated.

- CR is closed and stakeholders are informed.

Alternate paths

- A1: CR incomplete: returned to requester.

- A2: Rejected: reason recorded, requester informed.

- A3: Deferred: moved to a future release.

- A4: Emergency change (e.g. sensor malfunction, security flaw): fast-track by CCB chair, ratified later.

- A5: Verification fails: back to implementation, or rollback.

- A6: Impact beyond PM authority: escalate to the city corporations.

## Q4. Gantt Chart [6]

| ID | Task | Duration (wks) | Depends on | Weeks |
| --- | --- | --- | --- | --- |
| A | Requirements and feasibility | 3 | none | 1-3 |
| B | Architecture and design (IoT, cloud, app, security) | 4 | A | 4-7 |
| C | IoT bin sensors and firmware | 8 | B | 8-15 |
| D | Cloud platform and database | 8 | B | 8-15 |
| E | Analytics and route optimization (GPS, traffic, weather) | 6 | D | 16-21 |
| F | Mobile app (resident and collector) | 6 | D | 16-21 |
| G | Security and privacy implementation | 4 | D | 16-19 |
| H | System integration | 4 | C, E, F, G | 22-25 |
| I | System and load testing | 5 | H | 26-30 |
| J | Pilot deployment and UAT | 4 | I | 31-34 |
| K | Full rollout, training, handover | 3 | J | 35-37 |

(1 char = 1 week)
A Requirements    ###
B Design             ####
C IoT bins              ########
D Cloud + DB            ########
E Analytics/routes             ######
F Mobile app                   ######
G Security/privacy             ####
H Integration                        ####
I Sys + load test                        #####
J Pilot + UAT                                 ####
K Rollout/handover                                ###

Milestone reviews (city corporation updates): M1 design approved (week 7), M2 development complete (week 21), M3 integration done (week 25), M4 pilot accepted (week 34).

Critical path: A, B, D, E/F, H, I, J, K (37 weeks, about 8.5 months, matching COCOMO).

(Not required to use “#” for gantt chart. You can use lines as well. Also critical path, milestone, and Assumptions can be ignored if it is not mentioned in the question. )

Assumptions:

- Fri-Sat weekly holidays; 5-day work week.

- Government holidays (Eid-ul-Fitr, Eid-ul-Adha, Independence Day, Victory Day, Language Day, Pohela Boishakh) plus buffer.

- Monsoon can delay outdoor bin installation and field testing.

- Learning curve of 25 freshers; hardware delivery on time.

- Third-party traffic/weather APIs available.

## Q5. Review Method [5]

Justification

- Organization structure: 15 experienced engineers + 25 freshers across IoT, cloud and mobile teams, plus two city corporations as customers. A formal, role-based review gives seniors control over quality and mentors freshers.

- Aspect of task: Highly complex (IoT, real-time analytics, GPS routing), large (millions of users) and important (public service, privacy and security compliance). Defects found late are costly.

- Time: About 8.5 months with regular milestone reviews, so there is room to plan reviews at each milestone.

Appropriate review: Formal Inspection (not desk check, which is informal and individual, nor walkthrough, which is less rigorous).  (You can choose another review technique as well)

Activities

- Planning: moderator selects inspectors and schedules.

- Overview: author presents the artifact.

- Preparation: inspectors review individually using checklists.

- Inspection meeting: reader walks through, recorder logs defects.

- Rework: author fixes the defects.

- Follow-up: moderator verifies fixes and closes the inspection.

## Q6. KPAs and CMMI Level IV [5]

KPA (Key Process Area): A cluster of related practices that, performed together, achieve goals important for process capability at a maturity level.

Purpose: Show what an organization must do to reach a maturity level, give a common structure for assessment, and guide process improvement.

Current level: Level 3 (Defined). The organization runs a standard, documented process, tailors it per project, and does peer reviews and risk management. But performance is not measured statistically.

Target level: Level 4 (Quantitatively Managed).

|  | Level 3 (current) | Level 4 (target) |
| --- | --- | --- |
| Process | Defined and standardized | Measured and controlled with statistics |
| Management | Qualitative, proactive | Quantitative, data-driven |
| Predictability | Moderate | High (known process variation) |

Guidelines to reach Level 4 (compliance / rubrics)

- Organizational Process Performance (OPP): collect metrics (defect density, review efficiency, schedule variance, productivity), build baselines and performance models.

- Quantitative Project Management (QPM): set measurable quality and process goals; monitor sub-processes with statistical tools such as control charts.

- Identify special causes of variation and take corrective action with root-cause analysis.

- Maintain a central metrics repository and use it in estimation and milestone reviews.

- Train staff (especially the 25 freshers) in measurement and basic statistics.

- Keep all Level 3 practices in place (requirements, verification, risk, training).