# Project Management Mid Solution (Fall-25)

# Question1. Software Engineering Methodology:

Recommended Methodology: Agile (Scrum)

- Flexibility and Adaptability: Scrum allows for quick adjustments to project requirements as new challenges or technologies emerge.

- Iterative Development: Development is done in short sprints, enabling continuous improvement and early identification of issues.

- Cross-functional Collaboration: Facilitates teamwork among diverse experts like VR developers, AI specialists, and cybersecurity professionals.

- Prioritization of High-Value Features: Ensures critical features, such as astronaut training and real-time collaboration, are developed first.

- Risk Management: Short sprints help identify and mitigate risks early, ensuring critical aspects of the project are on track.

- Continuous Feedback: Provides regular opportunities for feedback and refinement, which is essential for a complex, mission-critical project.

Roles and Responsibilities:

- Product Owner:

  - Manages and prioritizes the product backlog.

  - Communicates project goals and ensures alignment with mission-critical features like astronaut training and real-time collaboration.

- Scrum Master:

  - Facilitates Scrum events (daily standups, sprint planning, reviews).

  - Removes obstacles, ensuring smooth progress and adherence to Scrum practices.

# Question 2. Vision and Scope Document:

A Statement of Work (SOW) outlines the scope, objectives, tasks, deliverables, and timeline of a project, serving as a guideline throughout its lifecycle.

Elements of SOW:

- Introduction

- Scope of Work

- Deliverables

- Timeline

- Resources Required

- Performance Criteria

- Assumptions and Constraints

Vision:
Develop a VR platform for real-time collaboration and astronaut training, integrating AI, mixed reality, and data visualization to enhance space mission support.

Scope:

  - Astronaut training simulations

  - Real-time collaboration between Earth and space teams

  - AI troubleshooting and prediction

  - Real-time spacecraft health monitoring

  - Cybersecurity and system integration

# Question 3. Work Breakdown Structure (WBS):

Rules for Generating a WBS:

- Decomposition: Break the project into smaller components for easy management.

- Hierarchical Structure: Organize tasks in levels, from major deliverables to detailed tasks.

- Clear Deliverables: Each component must have a defined output.

- Mutually Exclusive: Avoid overlapping tasks.

- Consistent Numbering: Use a clear numbering system for hierarchy.

- Clarity: Tasks should be easily understood.

- Activity Breakdown: If necessary, break down tasks further for better estimation.

Estimating Duration for Two Major WBS Components:

| WBS Code | Task Name | Subtasks | Duration |
| --- | --- | --- | --- |
| 1 | Project Management | Planning and Coordination | 2 weeks |
| 1.1 |  | Resource Allocation | 1 week |
| 1.2 |  | Risk Management | 1 week |
| 1.3 |  | Budget and Timeline Management | 1 week |
| 2 | System Design | VR Platform Architecture | 3 weeks |
| 2.1 |  | Mixed Reality Integration | 2 weeks |
| 2.2 |  | AI Troubleshooting System Design | 2 weeks |
| 2.3 |  | Data Visualization Tools | 2 weeks |
| 3 | Development | VR Training Modules (Spacewalks, Zero-Gravity) | 4 weeks |
| 3.1 |  | Real-time Collaboration Tools | 3 weeks |
| 3.2 |  | AI Algorithms and Predictive Systems | 4 weeks |
| 3.3 |  | Cybersecurity Implementation | 3 weeks |
| 4 | Testing | Alpha Testing (Initial Testing) | 2 weeks |
| 4.1 |  | Beta Testing (User Acceptance Testing) | 2 weeks |
| 4.2 |  | Performance and Stress Testing | 2 weeks |
| 5 | Deployment | Integration with Spacecraft Systems | 3 weeks |
| 5.1 |  | User Training for Astronauts and Engineers | 2 weeks |
| 5.2 |  | Final System Rollout | 2 weeks |
| 6 | Maintenance | Ongoing Support and Upgrades | Ongoing |
| 6.1 |  | Bug Fixes and Security Updates | Ongoing |

# Question 4. Delphi Wideband Estimation (DWE):

### Basic Course of Events for Delphi Wideband Estimation (DWE) Method:

- Formation of Estimation Team

- Preparation of Estimation Forms

- Individual Estimates

- Discussion of Estimates

- Convergence Process

- Final Estimate

| Task Name | Description | Estimated Duration by Team Member 1 | Estimated Duration by Team Member 2 | Estimated Duration by Team Member 3 | Estimated Duration by Team Member 4 | Estimated Duration by Team Member 5 | Average Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Management | Planning, coordination, and resource management | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks |
| System Design | Designing VR platform architecture, mixed reality integration | 3 weeks | 3 weeks | 3 weeks | 4 weeks | 3 weeks | 3.2 weeks |
| Development | Developing VR training modules and collaboration tools | 4 weeks | 4 weeks | 5 weeks | 4 weeks | 4 weeks | 4.2 weeks |
| Testing | Alpha, Beta, and Performance Testing | 2 weeks | 3 weeks | 2 weeks | 2 weeks | 2 weeks | 2.2 weeks |
| Deployment | Integration with spacecraft systems and user training | 3 weeks | 2 weeks | 3 weeks | 3 weeks | 3 weeks | 2.8 weeks |
| Maintenance | Ongoing support, bug fixes, and updates | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing |

Tentative Convergence Chart

| Iteration | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Average Duration |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 3 weeks | 3 weeks | 3 weeks | 4 weeks | 3 weeks | 3.2 weeks |
| 2 | 3 weeks | 3 weeks | 3 weeks | 3 weeks | 3 weeks | 3 weeks |
| 3 | 3 weeks | 3 weeks | 3 weeks | 3 weeks | 3 weeks | 3 weeks |

# Question 5. Risk Plan Sheet:

RMMM Concept (Risk Mitigation, Monitoring, and Management):   The RMMM concept focuses on identifying, analyzing, and mitigating risks throughout a project's lifecycle to ensure successful completion. It consists of three key components:

- Risk Mitigation: Strategies to reduce or eliminate potential risks. This involves taking proactive measures to minimize the likelihood or impact of risks.

- Risk Monitoring: Continuous tracking and assessment of identified risks to detect any changes or new risks that may arise during the project.

- Risk Management: The overall process of identifying, analyzing, and addressing risks through risk mitigation, monitoring, and developing contingency plans for unforeseen risks.

| Risk | Impact | Likelihood | Mitigation Strategy | Responsible Party |
| --- | --- | --- | --- | --- |
| Network Latency in Deep Space | High (Delays in communication and collaboration) | Medium | Develop a protocol for managing high-latency communication; use data compression techniques | Technical Team, Communication Experts |
| Cybersecurity Threats | High (Potential data breaches, compromised mission safety) | High | Implement strong encryption, multi-factor authentication, regular security audits | Cybersecurity Team |
| VR Simulation Discomfort for Astronauts | Medium (Discomfort affecting performance) | Low | Conduct thorough testing for comfort and adjust VR settings; provide breaks and health monitoring | VR Development Team, Health Experts |