# PMG 4101 – Mid-Term Exam (Spring-2024)

# Methodology & SCRUM Concepts:

Chosen Methodology: SCRUM (Agile Methodology)

For the development of the exam evaluation software, the SCRUM framework within the Agile methodology is the most appropriate choice. Here is the detailed explanation:

Rationale for Choosing SCRUM Methodology:

1. Complex and Evolving Requirements:

The project involves sophisticated features, such as AI integration for real-time monitoring, plagiarism detection, and performance benchmarking. Given the evolving nature of the features and potential adjustments as the project progresses, SCRUM allows for flexibility and adaptability.

The scope of the project includes multilingual capabilities and real-time exam monitoring, both of which might evolve based on user feedback. SCRUM supports these iterative updates and refinements throughout the development cycle.

2. Frequent Feedback from Stakeholders:

With diverse stakeholders, including learners, educators, and exam invigilators, frequent feedback is essential. SCRUM promotes continuous collaboration through regular sprint reviews, where stakeholders can assess the functionality of the software and provide input. This helps ensure the software aligns with user needs and expectations.

3. Incremental Delivery:

The project has a set timeline with specific deliverables (AI integration, multilingual support, etc.). SCRUM’s iterative approach allows the team to develop the software in manageable modules, delivering functionality incrementally. This ensures core features are available early in the development process and gradually improve over time.

4. Risk Management:

As the software integrates complex AI features, such as movement detection during exams, there are risks related to system integration and performance. SCRUM mitigates risks by breaking the project into smaller, testable chunks and allowing the team to address potential issues early in the development cycle.

5. Team Collaboration and Specialized Skills:

The project requires specialized skills, including AI engineers, ML specialists, and software developers. SCRUM fosters collaboration among cross-functional teams, allowing experts to contribute their knowledge and ensuring smooth communication across the project. This helps the team work cohesively on each component of the software.

Concepts in SCRUM Methodology:

Product Backlog:

The Product Backlog is a prioritized list of features, functionalities, and enhancements that the development team must work on to meet the project’s objectives. The backlog is constantly updated based on feedback from the client and stakeholders. In this project, the product backlog would include items like "AI-based exam monitoring," "automatic grading," and "plagiarism detection," with each feature broken down into smaller tasks or user stories.

Scrum of Scrums:

The Scrum of Scrums is a method used to coordinate multiple Scrum teams working on large projects. Each Scrum team conducts its own sprint planning, review, and retrospective meetings. The Scrum of Scrums is typically a meeting where representatives from each Scrum team meet to discuss their progress, challenges, and dependencies on other teams. In this project, if multiple teams are working on different features (e.g., AI integration, multilingual support, testing), the Scrum of Scrums can help align the efforts and ensure no duplication of work.

Drawbacks of SCRUM Methodology:

1. Over-Reliance on Collaboration:

SCRUM heavily depends on daily stand-ups, sprint reviews, and continuous collaboration among team members. If team members are spread across different locations or if communication channels are not strong, it may lead to delays and miscommunication.

2. Difficulty in Estimation:

Estimating the time and effort required for certain tasks, particularly for AI/ML integration and testing, can be challenging. SCRUM relies on story points and velocity, but predicting the exact effort for complex components may lead to inaccurate estimates.

3. Team Member Experience:

SCRUM requires all team members to be well-versed in Agile practices. If some team members lack experience, it may slow down the sprint process and affect the overall efficiency of the project.

When SCRUM is Ideal:

SCRUM is most beneficial in projects that have:

- Evolving requirements that need frequent changes or updates.

- Continuous stakeholder feedback and involvement.

- Short development cycles with the need for incremental delivery of features.

- High uncertainty or technological complexity, such as the integration of AI in real-time monitoring.

In contrast, SCRUM may not be appropriate for projects with fixed requirements or those requiring rigid, linear progression, such as projects that need to adhere to strict compliance or regulatory requirements without much flexibility.

# Project Plan and Vision & Scope Document:

Project Plan in Software Project Planning:

A Project Plan is a comprehensive document that outlines how a project will be executed, monitored, and closed. It defines the project’s scope, objectives, deliverables, timelines, resources, and risk management strategies. A good project plan ensures that all stakeholders are aligned, and the project stays on track, delivering the expected results.

The Project Plan typically includes:

- Project Scope: Defines what is included and excluded in the project. It outlines the deliverables, the work that needs to be done, and the criteria for success.

- Timeline and Milestones: Establishes a detailed schedule that includes all the tasks, phases, and milestones. This ensures the project is completed on time.

- Resources and Budget: Identifies the resources (e.g., human, technical, financial) required to complete the project and allocates a budget for each aspect of the project.

- Risk Management Plan: Identifies potential risks, their impact, and strategies for mitigating these risks. It includes how risks will be tracked and controlled throughout the project lifecycle.

- Roles and Responsibilities: Details the roles and responsibilities of all project members and stakeholders, ensuring accountability and clarity on tasks.

- Communication Plan: Defines how communication will be handled throughout the project, both internally and with external stakeholders.

- Quality Management Plan: Outlines the processes and standards that will be used to ensure the product meets the desired quality.

- Change Management Plan: Describes how changes to the scope, timeline, and other project parameters will be handled.

Vision Document Outline:

- Introduction:

- Project Overview: Development of an AI-powered exam evaluation software that automates grading, plagiarism detection, performance benchmarking, and real-time exam monitoring.

- Purpose: To revolutionize university-level education by providing an efficient, accurate, and comprehensive evaluation system.

- Scope: The project includes developing features for automated/manual evaluation, real-time monitoring, and multilingual support (English, Bangla, French).

- Stakeholders:

- Primary Stakeholders: University students, educators, and exam invigilators.

- Secondary Stakeholders: AI engineers, ML specialists, testing teams, and project managers.

- Objectives:

- Develop automated grading, plagiarism detection, and examination rules violation detection.

- Integrate AI for movement detection during exams to identify suspicious activities and send alerts to invigilators.

- Provide multilingual support in English, Bangla, and French.

- Deliver automated reports to provide feedback on student performance.

- Constraints:

- Tight timeline for the first release with some core features in 4 months.

- AI integration for real-time monitoring could be technically challenging.

- Ensuring system scalability to handle a large number of concurrent users during peak exam times.

Scope Document Outline:

- Project Scope Statement:

  - In-Scope:

    - Development of features like automated grading, real-time monitoring, plagiarism detection, and multilingual support.

    - Integration of AI for real-time exam monitoring.

    - Creation of a question bank management system.

    - Generating detailed feedback reports for students.

  - Out-of-Scope:

    - Features related to social learning tools or collaborative platforms will be considered in future releases.

- Functional Requirements:

  - Automated and Manual Evaluation: Grading based on predefined criteria and manual overrides.

  - Plagiarism Detection: Scanning student submissions for similarities with a question bank and external sources.

  - Real-Time Exam Monitoring: AI-driven movement detection to monitor students during exams.

  - Question Bank Management: A feature for managing exam questions and categorizing them based on difficulty and subject.

- Non-Functional Requirements:

  - Multilingual Support: The platform must support English, Bangla, and French initially.

  - Scalability: The system should be scalable to handle large volumes of students during exams.

- Assumptions:

  - All required resources, including AI engineers and ML specialists, will be available.

  - The system will be tested by both automated and manual testing teams.

- Exclusions:

  - Integration with social media platforms for collaboration or sharing exam results.

# WBS & Estimation:

WBS for the Project:

1. Platform Development:

- Task 1.1: Automated Evaluation System

- Develop the automated grading system.

- Create performance benchmarking framework.

- Develop rules for examination violation detection (e.g., cheating).

Estimated Duration: 15 days

- Task 1.2: Manual Evaluation System

- Develop manual grading and review system.

- Integrate with the automated system for cross-checking.

Estimated Duration: 10 days

- Task 1.3: Plagiarism Detection

- Integrate a plagiarism detection tool.

- Create a database of previous papers and resources.

Estimated Duration: 10 days

- Task 1.4: Question Bank Management

- Design and implement question bank management system.

- Enable question search, review, and modification.

Estimated Duration: 12 days

- Task 1.5: Real-Time Exam Monitoring

- Develop AI-based real-time monitoring system.

- Integrate movement detection to send alerts to invigilators.

Estimated Duration: 20 days

2. Language Translation and Multi-Lingual Support:

- Task 2.1: Translation of Interface

- Translate the entire platform interface (English to Bangla, French).

- Create language switcher options.

Estimated Duration: 10 days

- Task 2.2: Translation of Exam Content

- Translate exam content into Bangla and French.

- Validate translation accuracy.

Estimated Duration: 15 days

3. AI/ML Integration (For Future Use):

- Task 3.1: AI System for Self-Driving (Future Feature)

- Design AI for autonomous driving (future phase).

Estimated Duration: Deferred

- Task 3.2: Data Collection and Analytics for

- Collect data on student performance.

- Set up data analysis tools for AI model improvement.

Estimated Duration: 20 days

4. Security and Data Protection:

- Task 4.1: Secure Login and Authentication

- Implement secure login with MFA.

- Develop encrypted password storage.

Estimated Duration: 8 days

- Task 4.2: Data Encryption and Protection

- Implement data encryption protocols.

- Develop secure data storage and transmission methods.

Estimated Duration: 12 days

- Task 4.3: Secure Payment System Integration

- Integrate secure payment gateway.

- Ensure PCI-DSS compliance for payment data.

Estimated Duration: 8 days

5. Testing and Deployment:

- Task 5.1: Automated Testing

- Develop automated test cases for system functionalities.

Estimated Duration: 12 days

- Task 5.2: Manual Testing

- Conduct manual tests for usability.

Estimated Duration: 10 days

- Task 5.3: Bug Fixing and Optimization

- Address issues found during testing.

Estimated Duration: 12 days

- Task 5.4: Deployment

- Deploy the platform on production.

- Perform post-deployment testing.

Estimated Duration: 5 days

6. Future Enhancements (Optional):

- Task 6.1: Self-Driving AI Feature (Future Phase)

- Implement self-driving functionality (future phase).

Estimated Duration: Deferred

- Task 6.2: Social Learning Features

- Add discussion forums, live chats.

Estimated Duration: Deferred

Estimating Duration for Major WBS Components (in Days):

The estimated duration for the major WBS components is as follows:

Platform Development:

- Task 1.1: Automated Evaluation System - 15 days

- Task 1.2: Manual Evaluation System - 10 days

- Task 1.3: Plagiarism Detection - 10 days

- Task 1.4: Question Bank Management - 12 days

- Task 1.5: Real-Time Exam Monitoring - 20 days

Total for Platform Development: 67 days

Language Translation and Multi-Lingual Support:

- Task 2.1: Translation of Interface - 10 days

- Task 2.2: Translation of Exam Content - 15 days

Total for Multi-Lingual Support: 25 days

AI/ML Integration:

- Task 3.1: AI System for Self-Driving - Deferred

- Task 3.2: Data Collection and Analytics for AI - 20 days

Total for AI/ML Integration: 20 days

Security and Data Protection:

- Task 4.1: Secure Login and Authentication - 8 days

- Task 4.2: Data Encryption and Protection - 12 days

- Task 4.3: Secure Payment System Integration - 8 days

Total for Security: 28 days

Testing and Deployment:

- Task 5.1: Automated Testing - 12 days

- Task 5.2: Manual Testing - 10 days

- Task 5.3: Bug Fixing and Optimization - 12 days

- Task 5.4: Deployment - 5 days

Total for Testing and Deployment: 39 days

1.3 Estimated Total Project Duration (in Days):

Summing up the major components:

Platform Development: 67 days

Language Translation: 25 days

AI/ML Integration: 20 days

Security: 28 days

Testing and Deployment: 39 days

Total Duration: 179 days (~6 months)

# Delphi Wideband Estimation Technique:

The Delphi Wideband Estimation (DWE) technique is used for project estimation and is particularly useful for estimating the time or effort required for complex tasks. The process involves a group of experts who provide initial independent estimates, followed by group discussions and refinements until a consensus is reached.

This method helps achieve accurate estimates through collaboration and feedback from multiple experts. It is typically used for projects where uncertainty exists, and estimates need to be improved iteratively.

Basic Course of Events for Delphi Wideband Estimation

- Assemble a Team:

  - The project manager assembles a team of experts. In this case, the team consists of three members, each with knowledge of different aspects of the project (e.g., AI integration, security, software development, etc.).

  - Each expert is tasked with providing independent estimates of the time required to complete specific tasks in the project (e.g., "Develop car showcase module," "Integrate secure payment system," "Implement AI-based real-time exam monitoring").

- Initial Independent Estimation:

  - Each expert provides their independent estimate for the tasks based on their expertise.

  - Estimates are usually provided anonymously to avoid bias or influence from others.

- Group Discussion:

  - After the independent estimates are collected, the team meets for a group discussion. In this meeting, each expert explains the rationale behind their initial estimates. They also discuss any ambiguities or uncertainties that might affect the estimates.

  - The goal is to share knowledge and assumptions to reach a clearer understanding of the task at hand.

- Re-estimation and Refinement:

  - Based on the group discussion, the experts revise their estimates. This process allows them to refine their estimates with the benefit of additional insights and clarifications from their peers.

  - This is an iterative process that continues until the estimates converge.

- Final Estimation and Consensus:

  - After the discussion and refinements, the experts agree on a final estimate for each task. This is the agreed-upon number that will be used for project planning, scheduling, and resource allocation.

  - If needed, a tentative convergence chart is created to visualize the progress of the estimates as they move toward consensus.

Steps of Estimation Session

1. Estimation Session (with Individual Form Shows Iterations)

In the estimation session, each expert provides an estimate, which is refined over multiple rounds.

- Initial Round:

  - Expert 1 estimates: 10 days

  - Expert 2 estimates: 12 days

  - Expert 3 estimates: 14 days

- Second Round (after discussion):

  - Expert 1 revises to: 11 days

  - Expert 2 revises to: 12 days

  - Expert 3 revises to: 13 days

- Final Round (after further refinement):

  - Expert 1 estimates: 12 days

  - Expert 2 estimates: 12 days

  - Expert 3 estimates: 12 days

  - Final Consensus: 12 days

This process helps narrow down the range of estimates and converges on a realistic duration for the task.

2. Assemble Task for the Project

The tasks are assembled based on the WBS (Work Breakdown Structure) created for the project. Examples of tasks include:

- Task 1: Develop the car showcase module.

- Task 2: Integrate secure payment gateway.

- Task 3: Implement AI-based real-time exam monitoring.

Each task will be assigned an estimate from the experts. In the case of the Delphi Wideband Estimation, multiple rounds of estimation and discussion will help refine these initial estimates to more accurate final values.

Tentative Convergence Chart of Duration

The convergence chart visualizes how the estimates from the experts evolve over time. It helps track how much the estimates change after each discussion and shows when they reach consensus.

Example of Convergence Chart for Task 1:

| Iteration | Expert 1 Estimate | Expert 2 Estimate | Expert 3 Estimate | Final Estimate |
| --- | --- | --- | --- | --- |
| 1st Round | 10 days | 12 days | 14 days |  |
| 2nd Round | 11 days | 12 days | 13 days |  |
| Final | 12 days | 12 days | 12 days | 12 days |

In the final estimate, the experts converge on 12 days for the development of the "car showcase module" after multiple rounds of discussion and refinement.

Conclusion

The Delphi Wideband Estimation (DWE) technique is a powerful method for estimating the effort and duration required for tasks in complex projects. By bringing together experts from various domains, the process enables the team to generate realistic estimates, refine those estimates, and reach consensus. This iterative approach ensures that the final estimates are accurate and based on informed input from all relevant stakeholders.

# Risk Mitigation & Risk Plan:

| ID | Risk (what could go wrong) | Probability | Impact | Priority | Triggers / Indicators | Mitigation & Response | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | AI proctor false positives or negatives unfairly flag or miss cheating during real-time monitoring | 3 | 5 | 15 | False-positive rate > 5%, student appeals spike, high proctor override rate | Reduce: multi-signal fusion (gaze, motion, audio), threshold tuning, calibration runs; human-in-the-loop review; gold-set evaluation each sprint; safeguard with manual override and appeal workflow | AI Lead |
| R2 | Privacy or compliance breach with video and audio data (consent, retention, cross-border transfer) | 3 | 5 | 15 | Legal inquiry, DPO concerns, unclear retention map, vendor without DPA/SCCs | Avoid/Reduce: DPIA, explicit consent flows, regional storage, encryption at rest and in transit, role-based access; Transfer: vendor DPAs and SLAs; Accept: emergency privacy mode that disables camera capture if compliance risk is detected | Compliance Officer |
| R3 | Load or performance failure at peak exam windows (timeouts, dropped proctor streams) | 3 | 5 | 15 | 95th percentile latency above target, CPU saturation, stream drop > 2% | Reduce: capacity modeling, load tests with exam-day traffic shape, autoscaling, CDN, circuit breakers; Accept: read-only degrade of analytics; Transfer: CDN and cloud provider SLAs | DevOps Lead |
| R4 | Scope creep: extra languages or features squeezed into the same deadline | 4 | 4 | 16 | Frequent change requests, sprint spillovers, burn-down flatlines | Avoid/Reduce: Change Control Board, MoSCoW priority, release train, feature flags; Accept: schedule buffer; Transfer: contractual statement of work updates | Project Manager |
| R5 | Recruitment delay for AI or ML engineer blocks the proctoring module | 3 | 4 | 12 | Open role > 30 days, missed AI spikes | Reduce: parallel vendor shortlist, interim contractor, narrow MVP with manual review first, move advanced ML to Phase 2 | Engineering Manager |
| R6 | Third-party dependency outage (plagiarism API, translation, payment) | 3 | 4 | 12 | Provider status red, 5xx spike, quota near limit | Reduce/Transfer: multi-provider fallback, result caching, graceful degrade with retry queue; vendor SLAs and credits | Platform Lead |
| R7 | Security incident (exam data leak or account takeover) | 2 | 5 | 10 | Vulnerability backlog above threshold, failed penetration test checks | Reduce: secure development lifecycle, secrets management, SSO/MFA, penetration test per release, backups with immutability; Transfer: cyber insurance | Security Lead |
| R8 | Device or browser incompatibility for cameras or microphones (WebRTC issues) | 3 | 4 | 12 | High failure rate in pre-exam checks, specific OS or browser cluster of bugs | Reduce: supported device matrix, pre-exam self-check tool, fallback capture pipeline, test lab with top devices | QA Lead |
| R9 | Localization quality problems in Bangla or French affecting clarity of rules and UI | 3 | 3 | 9 | High help-desk contacts from localized cohorts, poor LQA scores | Reduce: professional translators, glossary and translation memory, LQA rounds; Accept: post-release hotfixes via CMS | Localization Lead |
| R10 | Ethical or reputation risk: surveillance concerns or model bias | 2 | 4 | 8 | Negative student feedback, media escalation | Reduce: publish model card, transparency UX, opt-in pilots, bias tests across demographics; Accept: clear appeal process | Product Owner |